Table of Contents

# EdVidura — Process from Start to Finish: Lovable to Backend

| Field | Value |
| --- | --- |
| Version | 3 — 23 October 2026 (draft for approval) |
| Replaces | Version 2, 23 October 2026, which replaced the Lovable Build Pack |
| Owner | Senior developer (name to fill) |
| Approver | Product owner (name to fill) |
| Audience | Product owner, senior developer, designer, front-end developer, instructional designer, QA, security / data-protection officer (DPO), junior developers |
| Purpose | The order of work from a recorded baseline to a released, verified EdVidura build: who does each step, which gate it passes, and how anyone knows it worked. Use it with the FINAL features and prompt documents. |
| Status of facts | Written without the FINAL files open. Every statement about a FINAL file carries a VER number and must be checked before this version is approved. |

What changed from Version 2:

- Environments and access (§0A) and roles with sign-offs (§0B) are new.

- The demo password is rotated in Phase 0, not at release.

- A confirmed live exposure follows an incident path at once.

- Decisions are grouped by what they block.

- The backend contract gains the columns that break integrations, and covers routes with no screen.

- Lovable set-up matches how Lovable works today.

- Templates are changed, not rebuilt.

- There is a Definition of Done for every screen (§6.3) and a test plan covering tenant isolation, grade passback and the LTI environment matrix.

- Learning-design checks run through every phase.

- Release covers rollout, rollback, monitoring and the learning-gain baseline.

- Gates are per batch (Appendix A), with re-entry rules (§11) and a critical path (§12).

The full list of changes is in the Change Table.

## How to read this

- Steps are numbered. Each is one action with a result you can see. Do them in order unless the step says it can run in parallel.

- Gates close a phase or a batch. Each gate names its evidence and who signs it. If the evidence isn’t in the tracker, the gate is not closed.

- IDs:

  - DEC-nn is a decision.

  - VER-nn is a check to verify.

  - R1–R5 are the release gates.

  - Screen IDs (SH-, LR-, TC-, SA-, OP-) and batch IDs (Batch 0, S1–O1) are the same as in the features and prompt documents.

- Stop and ask lines mark where judgement is needed. When you reach one, stop and ask the senior developer before you continue.

- The tracker is the live record. This document says what to record; the tracker holds the result.

# 0. Which files to use

| File | Version · date · owner | Use it for | Status |
| --- | --- | --- | --- |
| EdVidura_Combined_Summary_and_Differences_v2.docx | v2 · to fill · to fill | Read first: what each document says, which value is correct, and why | Current |
| EdVidura_Features_Document_FINAL.docx | to fill | What every screen does; the route inventory (Appendix A); the screen list with routes and templates (Appendix C); findings and reconciliations | Current |
| EdVidura_Lovable_Prompt_Document_FINAL.docx | to fill | The prompts: authority section, Part 0, Batch 0, batches S1 to O1, Addendum V | Current |
| EdVidura_Audit_Report_Verification.docx | to fill | Which claims in the audit report are true, partly true, false, or need a live check | Current |
| EdVidura_Enhancement_Tracker_reviewed.xlsx | to fill | Decisions, checks, findings, changes, the API Contract tab and the Gate Matrix tab. Keep it current at every phase | Current — the live record |
| EdVidura Learning Design & Transformation Standard | v1.0 · 22 Oct 2026 · to fill | Learning purpose, learner vocabulary, AI tutoring rules, learning-design checks | VERIFY (VER-66) |
| EdVidura Developer Field Guide — “Careful Here” | 22 Oct 2026 · to fill | Rules of the codebase, mistakes to avoid, how to test, glossary | VERIFY (VER-66) |
| EdVidura_Package_Review_and_Dossier_Verdict.docx | to fill | Why the Production Ground-Truth Dossier is not used | Reference |
| EdVidura_Lovable_Build_Pack.docx | — | Superseded by this document | Do not use |
| superseded/ folder | — | Earlier versions | Do not use |
| edvidura_walkthrough.py | to fill | Live sign-in check for the three role accounts | Run it yourself, after review (Phase 0 step 3) |

Never use:

- the dossier, for any wording, route, token or banner;

- any path under /static/uploads/... (tenant uploads such as extracted eBook files), in any screen, prompt or link;

- /requirements-board or /session-today;

- any password, key or token, in any document.

The app’s own build assets (stylesheets, scripts, fonts) may still be served from a static path. The ban covers tenant uploads only. VERIFY what /static serves before acting on DEC-28 (VER-55).

# 0A. Environments, accounts and access

Owner: senior developer. Decision: DEC-35 (environments) and DEC-34 (live checks).

| Environment | What runs there | Data | Who has access |
| --- | --- | --- | --- |
| Local | Docker Compose: app, database, a containerised Moodle | Synthetic only | Each developer |
| Staging | Same build as production, with its own Moodle and two demo institutes | Synthetic learners in demo institutes; never real learner data | Build team; designer for visual checks |
| Production | The live deployment (host recorded in Phase 0 — VER-65) | Real institutes and learners | Senior developer; others only for an approved check |

Rules:

- Use role accounts, not personal ones. Run checks with the demo accounts: learner, instructor and Training Officer (school admin), plus a second institute’s learner for cross-tenant tests. Refer to them by role in every document.

- Keep credentials in the team’s secrets manager. Never put them in a document, chat, ticket, screenshot or script file.

- Run checks on staging first. A check runs on production only if it cannot be answered on staging, it is read-only, and the product owner has approved it in writing (DEC-34).

- Log every production check: who, when, what was requested, and the result. List any check made while logged out (unauthenticated) before you run it.

- Give each person the least access they need. The designer works on staging. Production access is not needed for visual checks.

Stop and ask the senior developer if a check seems to need production, real learner data, or an account you don’t have.

# 0B. Roles, responsibilities and sign-off

R = does the work · A = accountable, signs · C = consulted · I = informed.

| Phase | Product owner | Senior developer | Front-end dev + designer | Instructional designer · QA · DPO · juniors |
| --- | --- | --- | --- | --- |
| 0 Baseline | I | A, R | I | Juniors R (test run, paired); DPO I |
| 1 Live checks | C (approves production checks) | A, R | Designer R (staging visuals) | QA C; DPO C on exposures |
| 2 Decisions | A | R | C | Instructional designer C on learning decisions; DPO C on data decisions |
| 3 Backend contract | I | A | Front-end R (mock alignment) | Juniors R (contract rows, paired); QA C |
| 4 Lovable prototype | I | A (gate) | R | Instructional designer C (learning intent); QA C; juniors R (screenshots, checks) |
| 5 Connect | I | A | Front-end R | Juniors R (templates, tests); QA C; instructional designer C (DoD item 8) |
| 6 Live verification | I | A | C | QA R; DPO C; instructional designer R (learner-loop walk-through) |
| 7 Release | A | R | C | QA, DPO and instructional designer sign R1–R5 as listed in §8.1 |
| 8 Keep current | I | A, R | R (prototype and prompt document) | All update the tracker for their own work |

Sign-off per gate is in Appendix A. A gate is signed in the tracker with name and date. A signature means “I have seen the evidence”, not “the work was done”.

# 1. Phase 0 — Establish the baseline (before anything is built)

Owner: senior developer. Output: a baseline record in the tracker (VER-01), plus VER-59, VER-62 and VER-65.

- Rotate the demo password now. It has appeared in at least one document (the audit report). Removing the text does not stop it working.

- Search for copies of the old password in documents, repository history, chat, shared drives and tickets. Remove them, and record where they were (VER-59).

- Confirm each environment uses different credentials. Store the new ones only in the secrets manager.

- Review edvidura_walkthrough.py before running it. Record what it does with credentials, which hosts it calls, and where it writes its report and screenshots (VER-62). Do not run a script you have not read.

- Start the application from the repository (Docker Compose, local).

- Run the full test suite. Record the number passed, failed and skipped, the date, and the commit SHA. The earlier counts (265 and 295) are historical. Do not quote them until re-run.

- Deal with the two files reported modified in the last audit (app/modules/xapi/service.py, templates/integrations.html): commit, revert or record them, with the senior developer’s review.

- Run edvidura_walkthrough.py against staging with the three role accounts. Run it on production only under DEC-34.

- Store REPORT.md and the screenshots securely. Use an access-controlled folder; they may show learner data. Do not paste them into chat or into the documents folder.

- Record the production EdVidura host (audit claim 23, now VER-65) and the environment list from §0A.

Gate (G-PRE, part 1): baseline recorded with environment and commit; password rotated and copies listed; walkthrough script reviewed. Without the baseline, every “Code-present” in the documents stays unproven. Signs: senior developer.

Stop and ask the senior developer if the app doesn’t start, tests fail in a way you can’t explain, or you find the old password anywhere you can’t remove it yourself.

# 2. Phase 1 — Live checks that change the design

Owner: senior developer, with the designer for visual checks on staging. Output: each result recorded in the tracker as Confirmed, Disproved or Open, with evidence. These checks can run in parallel with Phase 3 (§12).

## 2.1 Checks

Run on staging first. Use production only under DEC-34.

| Check | Account · environment | Why it matters | Tracker |
| --- | --- | --- | --- |
| Is there a “Top Learners” table on school analytics? | Training Officer · staging | It would rank learners — a leaderboard. If it exists, it is removed unless the product owner records a reason. | VER-64 (audit claim 8) |
| What does the time-capsule download contain? | Instructor · staging | A data export: format, tenant scope and personal data | VER-61 (audit claim 7) |
| After Feedback Assist, does any grade reach Moodle? | Instructor · staging | Must be copy-only unless the product owner decides otherwise | VER-63 (audit claim 6) |
| Does an unauthenticated request for an extracted eBook file under /static/uploads/epub/ succeed? | Logged out · production (approved, logged) | Public exposure of learner content. If yes, follow §2.3 now. | VER-45 |
| Are /requirements-board and /session-today reachable logged out? | Logged out · production (approved, logged) | Internal pages exposed. If yes, follow §2.3 now. | VER-46 |
| Do the lesson, quiz and Ask Vidura screens show the exact labels and banners in Addendum V? | Learner, instructor · staging | Confirms the verified specifications | VER-48 |
| Does learner activity show “LRS” or “Tier”? | Learner · staging | System terms must not reach learners | VER-49 |
| Does a quiz result show the extra banner the dossier describes? Name the banner text from the Audit Report Verification before checking. | Learner · staging | Settles a dossier claim. The dossier itself is still never a source for wording. | VER-50 |
| Does a themed page use a tenant accent, and which hue does each demo tenant get? | Any · staging | Contrast and tokens (DEC-31) | VER-47 |
| Do RLS policies exist on institutions and lti_platforms in the live database? | Database · production (read-only, approved) | Tenant isolation (DEC-29) | VER-44 |

## 2.2 Checks carried in from earlier registers

These block safe integration. Either they have been closed in the FINAL documents or the audit verification (record where), or they run in this phase. Confirm which applies (VER-53, VER-54).

| VERIFY | What to confirm |
| --- | --- |
| VER-02, VER-03 | How LTI role claims map to instructor and Training Officer, and whether instructor routes check course context |
| VER-07, VER-08, VER-09 | RLS enabled and forced on every tenant table; tenant set with SET LOCAL; background workers set tenant context |
| VER-10 | EPUB extraction guarded against zip-slip; EPUB content served safely |
| VER-13 | CSV exports neutralise formula characters |
| VER-20 | Grade passback (AGS): keyset reachable from Moodle, key ID, clock, token endpoint |
| VER-36, VER-37 | CSRF protection on form and JSON posts; framing limited to the registered Moodle origins |
| VER-38 | What happens to quiz answers when the session expires before submit |

## 2.3 Incident path for a confirmed exposure (DEC-33)

INCIDENT — a learner file, internal page or secret is reachable
when it should not be

1. Stop checking. Tell the incident lead (senior developer)
   and the DPO at once.
2. Contain: block the path, disable the route or rotate the
   secret, within the same working day.
3. Record: what was reachable, since when (if known),
   which institutes, what personal data.
4. Assess: the DPO decides whether this is a personal-data
   breach under the DPDP Act and Rules, and who must be told,
   by when.
5. Fix properly: the permanent change (for example, DEC-28)
   goes through review.
6. Re-test the same request and record the evidence.
7. Close the incident in the tracker, with the DPO's sign-off.

Do not wait for Phase 2 or release to contain an exposure.

## 2.4 Evidence format (every check, every phase)

Record: environment, commit SHA, account role (never the account name or password), date and time (IST), the exact request or steps, the result, and a screenshot or HTTP log stored in the access-controlled evidence folder.

## 2.5 Gate

VER-44 to VER-50 and VER-61, VER-63, VER-64 are recorded with evidence. VER-53 and VER-54 are answered. Any result that differs from what the documents say — Confirmed or Disproved — and affects a screen goes to Phase 2 before that screen is built. Signs: senior developer.

Stop and ask the senior developer if a check would need you to change data, use production without approval, or if a result looks like an exposure.

# 3. Phase 2 — Decisions

Owner: product owner and senior developer. Output: Decision Log entries signed in the tracker, with decider and date. Learning decisions also have an instructional-design reviewer. Data decisions also have the DPO.

## 3.1 Decisions, grouped by what they block

Before any batch (gate G-PRE):

| Decision | Recommendation | Blocks | Signs |
| --- | --- | --- | --- |
| DEC-01 Production front end | Open until VER-52 confirms it in the tracker. Default until then: the Lovable output is a design reference, and the production front end stays server-rendered (Jinja). No generated code enters the FastAPI repository. | Phases 4 and 5 | Product owner + senior developer |
| DEC-27 Design baseline: Citrus Mint from the code; Indic font fallbacks | Adopt, after the contrast check (VER-57) | Part 0, Batch 0 | Product owner + designer |
| DEC-08 UI terminology (School / Institute; School admin / Training Officer; Teacher / Instructor; Student / Learner) | Choose one set, once | Every batch | Product owner |
| DEC-16 One learner vocabulary (one name per concept) | Adopt the vocabulary table; backend codes never shown to learners (rule 3.2.1) | Every batch | Product owner + instructional designer |
| DEC-32 Lovable workspace: plan, access, public remixing, who may push, branch protection, credit budget | See §5.1 | Phase 4 | Senior developer + product owner |
| DEC-35 Environment model | Local, staging, production (§0A) | Phases 1, 4–6 | Senior developer |
| DEC-39 Change control for companion documents during the build | Build each batch against a named version (§9) | Phase 4 | Senior developer |

Before specific batches:

| Decision | Recommendation | Blocks | Signs |
| --- | --- | --- | --- |
| DEC-31 Tenant accent contrast | Clamp accent lightness so white text passes 4.5:1. Also check accent text on page and surfaces (4.5:1) and accent focus or control edges (3:1), for all six hues (VER-57). | Batch 0, any themed screen | Designer + front-end developer |
| DEC-38 (formerly G4) Stickers, teleport link, report-a-problem | Omit stickers (no gamification). Add the teleport link and report-a-problem only after VER-60 and a privacy note: what is collected, who sees it, how long it is kept. | Batch 0 shell, L2 | Product owner + DPO |
| DEC-30 Pass mark as a constant (60%) | Keep the constant for now. Say on screen where 60% comes from. A per-course threshold goes on the Pedagogy Roadmap. | L2, L6 | Product owner + instructional designer |
| DEC-28 Public /static mount | Move tenant uploads behind authenticated, tenant-scoped routes. Keep build assets public. VER-55 first. | L1, L7, L8, T1 and any screen that shows a file | Senior developer |
| DEC-04 Menus for someone who is both instructor and Training Officer | Show both groups | Batch 0, A1 | Product owner |
| DEC-02, DEC-03, DEC-05, DEC-09, DEC-10, DEC-18, DEC-26 | As in the Decision Log; confirm status (VER-53) | Batches listed in Appendix A | As in the Decision Log |

Before release (gates R2–R5):

| Decision | Recommendation | Blocks | Signs |
| --- | --- | --- | --- |
| DEC-29 RLS on institutions and lti_platforms | Decide each table against the criteria in 3.2.3 | R2 | Senior developer + DPO |
| DEC-19, DEC-21, DEC-22, DEC-24, DEC-33, DEC-34 | As in the Decision Log | R2, R3 | As in the Decision Log |
| DEC-17, DEC-37 | Learning-gain baseline before learners start; staged rollout (§8.2) | R4, R5 | Product owner + instructional designer |
| DEC-36 Definition of Done per screen | Adopt §6.3 | R1 | Senior developer + QA |

## 3.2 Rules that come with the decisions

- Display mapping (DEC-16). Code values stay in data. Learners and instructors see words from the strings file. A backend value such as an enum, a state flag or a role code is never printed on a screen as it is. Every new value gets a display string before its screen is built.

- Assets and uploads (DEC-28). “Never use /static/...” means tenant uploads. The app’s own stylesheets, scripts and fonts keep their path unless VER-55 shows they must move.

- RLS criteria (DEC-29). For each table, record:

  - what reads it, before tenant resolution and after;

  - whether any user should ever see another institute’s row;

  - which database role reads it;

  - which test proves the answer.

- lti_platforms is read to find the tenant, so it may need a narrow exception. Write that exception down; don’t assume it.

- Top Learners (VER-64). If it exists, remove it unless the product owner records a reason. Ranking learners against each other conflicts with the Learning Design Standard (no leaderboards; ethical analytics).

## 3.3 Apply signed decisions before pasting

- When a decision changes a label, a token, a step or a screen, update the Lovable prompt document as a new version (for example FINAL-r2), with a Change Log row.

- Record that version in the tracker against each affected batch.

- Only then may the batch be pasted. Batches are always pasted exactly as written in the recorded version (§5.2).

## 3.4 Gate

Every decision in the “before any batch” table is signed before Batch 0. A batch-specific decision is signed before its batch (Appendix A). Release decisions are signed before the matching release gate. Signs: product owner and senior developer; the instructional designer and DPO countersign where shown.

# 4. Phase 3 — Backend contract (the main defence against data-shape defects)

Owner: senior developer. Output: the “API Contract” tab in the tracker. Contract rows are written by junior developers, paired, and reviewed by the senior developer.

Why: the Lovable batches are built with mock data. Mock data that does not match the real responses is the main source of data-shape defects when screens are connected. (Other integration defects come from authentication, cookies inside the Moodle iframe, CSRF and tenancy; those are covered in Phase 6.) Each mock is shaped from the contract, and the contract from the code. Field names are copied from the code, not from the documents.

Start from: Appendix A of the features document (all routes, with method, path, handler, guard and template) and Appendix C (screens). VERIFY the route count against Appendix A.

## 4.1 Contract columns

| Column | What to record | Source |
| --- | --- | --- |
| Screen ID | e.g. LR-06, or “none” for routes without a screen | Appendix C |
| Method and path | e.g. GET /quiz/result/{attempt_id} | Appendix A |
| Kind | JSON endpoint · server-rendered page · form post · file export | Handler |
| Guard and scope | Guard (signed-in, instructor, school admin, ops) and data scope (own records, course, institute) | Handler and query |
| Session and auth | Cookie or LTI context needed; behaviour on expired session | Middleware, handler |
| CSRF | Token field name, or “none” (then raise a finding) | Template, middleware |
| Request fields | Name, type, required or not, limits | Handler parameters, form fields |
| Response or context fields | Name, type, nullable or not. For pages: the template context variables. | Return value or template context |
| Enumerations and states | Every allowed value (for example the grade states), and its display string | Code; strings file |
| IDs shown | Which identifiers may appear on screen (normally none) | Rule |
| Time | Stored in UTC, shown in IST; format | Code |
| Limits | Page size, upload size and type, rate limits | Code, config |
| Errors | Real status code and template for denied, missing and other-institute records (VER-56) | Handler; staging test |
| Empty states | What the screen gets when there is no data | Handler |
| Mock file | The module in the Lovable project, named by convention (§4.5) | Convention |

## 4.2 Worked examples

The field names below are illustrative — copy the real names from the code.

JSON endpoint — /learn/coach/ask (LR-07 drawer):

- Method and guard: POST, signed-in learner, own course only.

- Session: session cookie inside the Moodle iframe; an expired session must return a clear error the drawer can show.

- CSRF: a token field or header.

- Request: question (string, max length from code), lesson_id (optional).

- Response: answer (string), check_question (string or null), sources (list of lesson titles; may be empty), grounded (boolean).

- Display rule: “From your class lessons” appears only when sources is not empty.

- Errors: model unavailable; graded quiz open (DEC-10).

- Mock: coach.ts.

Server-rendered page — LR-06 quiz result:

- Method and guard: GET /quiz/result/{attempt_id}, signed-in, own attempt only.

- Context: attempt (score, total, attempt type practice or graded), rows (question, chosen answer, correct answer, correct flag), grade_sent, grade_error, ags_available.

- Enumerations: the four gradebook messages and their display strings (Addendum V).

- Errors: another learner’s or another institute’s attempt returns the access page (VER-56).

- IDs shown: none.

- Mock: attempts.ts.

Form post — POST /quiz/submit (LR-05):

- Form fields: one radio group per question (name pattern from the template), CSRF token, attempt type.

- On success: redirect to the result page.

- On expired session: VER-38 — record whether answers survive.

- Errors: missing answers, quiz closed.

- Mock: quiz.ts (the submit result is simulated).

## 4.3 JSON endpoints and file exports

Record each one’s real request and response or file content.

- JSON:

  - /learn/coach/ask, /learn/coach/feedback, /learn/coach/shortcuts;

  - /api/v1/manuals/{manual_id}/progress, /api/v1/manuals/{manual_id}/bookmarks, /api/v1/manuals/{manual_id}/annotations;

  - /teacher/analytics.json, /teacher/analytics/live.json, /school-admin/analytics/live.json;

  - /quiz/result/{attempt_id}/receipt.json;

  - /teacher/time-capsule.json.

- File exports (CSV): /teacher/analytics.csv, /teacher/attempts.csv. Formula characters must be neutralised (VER-13).

## 4.4 Routes without a screen

These can still break the integration or leak data. Give each a contract row with “Screen ID: none”:

- LTI: login initiation, launch, JWKS (keyset), deep-link return, AGS score post, NRPS roster sync, return-to-Moodle (/return-to-lms, /return-to-moodle).

- Onboarding: /onboard, platform activation (/onboard/platform/{id}/active), /lti/register.

- Operations: /ops/retry-lrs, /school-admin/integrations/retry-lrs.

- Data exports:

  - /quiz/result/{attempt_id}/receipt.json — learner-facing. The button must not say “JSON” (“Download receipt file”), and the file must not contain internal IDs (VER-40).

  - /teacher/time-capsule.json — exports class data. Record which personal data it holds, its institute scope, and who may download it (VER-61).

  - The CSV exports in §4.3.

## 4.5 Align the Lovable mock data with the contract

The Lovable prompt document’s Batch 0 already defines mock modules, written from the documents. Before Batch 0 is pasted:

- Compare each mock module with the contract rows for the screens that use it: field names, types, nullability, enumerations, counts.

- Update Batch 0’s mock-data section in a new version of the prompt document (§3.3) wherever they differ. Record each change in the Change Log.

- Generate the TypeScript mock types from the contract (or check them against it with a script), so later drift is caught automatically.

- Naming convention: one module per entity in src/data/, named after the entity (attempts.ts, lessons.ts, coach.ts …). Use the same names in the contract’s “Mock file” column.

## 4.6 Contract tests

Add backend tests that fail when a response or template context loses, renames or re-types a field in the contract. Run them in CI (§7.1).

## 4.7 Gate

A batch may start when every screen in that batch has a complete contract row and its mocks match (§4.5). Phase 3 is complete when every Appendix C screen and every route in §4.4 has a row. Signs: senior developer.

Stop and ask the senior developer if a handler’s real fields differ from the features document, a route has no guard, or an endpoint returns data from more than one institute.

# 5. Phase 4 — Build the prototype in Lovable

Owner: designer and front-end developer; senior developer signs each batch gate. Output: an accepted, tagged prototype state per batch, recorded in the tracker.

## 5.1 Lovable set-up (DEC-32)

These steps were checked against Lovable’s documentation on 23 October 2026. Lovable changes often; re-check before set-up (VER-58).

- Create one Lovable project in a workspace used only by the build team.

- Set the project’s access level.

  - Use Restricted (invited users only) if the team’s plan offers it; at the time of checking, that is the Business and Enterprise plans.

  - Otherwise keep the default Workspace access in that dedicated workspace.

  - Record the plan and the access level in the tracker.

- Turn public remixing off. When it is on, anyone with the link can see a preview and copy the project.

- Connect the project to a new GitHub repository (Lovable creates a new repository; it cannot import one).

  - Git sync is two-way. Lovable pushes its edits to the synced branch. Commits pushed to that branch by anyone appear in the Lovable project.

  - If histories diverge, Lovable pushes to a separate lovable-sync branch instead.

- Protect the synced branch:

  - only the Lovable app and the senior developer may push;

  - no force-push or history rewriting;

  - no direct edits by anyone else.

- Do not connect any backend, database, authentication or cloud service in Lovable. The prototype uses mock data only. If Lovable offers to add one, decline, and say the prototype must not call any backend.

- Put Part 0’s hard rules in the project’s persistent instructions (Lovable’s project Knowledge) as well as pasting Part 0. This reduces drift over long sessions.

- Set a credit budget per batch and record credits used per batch in the tracker.

- Build in Batch 0 the shell and shared components. The order follows the FINAL prompt document: Part 0 (master prompt), then Batch 0. VERIFY which of the two produces the working shell (VER-51), and do not start S1 until the shell exists and passes Batch 0’s checklist.

## 5.2 The per-batch routine

Work in the order of the Lovable document: Batch 0, then S1 to S3, L1 to L8, T1 to T7, A1 to A2, O1. Move to the next batch only after the previous one is accepted.

- Check the batch’s gate in Appendix A. Its decisions are signed, its VERIFY items recorded, its contract rows complete, and the prompt-document version recorded.

- Tag the last accepted state on the synced branch (for example accepted-S2). This is your revert point.

- Paste the batch exactly as written in the recorded prompt-document version. Do not edit route paths or label text in Lovable. Changes go through §3.3.

- Check dependencies and environment files against the previous tag:

  - package.json and the lock file;

  - any .env* file;

  - any supabase/ or other backend folder.

- Any new backend, authentication, analytics or HTTP-client package is a rejection.

- Run the acceptance checklist (§5.3) and the screenshot script.

- If something is wrong, send one correction message naming the batch and the single problem. Do not ask Lovable to “fix everything”.

- After two failed corrections on the same problem, revert to the last accepted tag and re-prompt a smaller part of the batch. Record the credits used.

- Do not use Lovable’s visual editor or drafts to change accepted screens. If one is unavoidable, record it in the Change Log as a prompt change.

- When the batch passes, tag it (for example accepted-S3), record the tag and commit SHA in the tracker against the batch, and add a Change Log row.

## 5.3 Acceptance checklist for every batch

- Batch 0’s common checklist (items 1 to 19 in the Lovable document; VERIFY numbering in FINAL).

- Screenshots at 375, 768 and 1280 px for every screen and state in the batch, taken by a script (for example Playwright against a local build of the synced repository), and stored with the tag name.

- Keyboard pass through every control, in order.

- Screen-reader spot check with one of NVDA, TalkBack or VoiceOver.

- Network check: during mock flows, the browser’s network panel shows no request to any API, authentication, database or third-party data host. The app’s own scripts, styles, self-hosted fonts and the preview tool’s own connections are allowed.

- Labels: every label matches the batch text, the authority section or Addendum V. No label comes from the dossier.

- Mock data: every mock shape matches the Phase 3 contract for the screen.

- Paths: no route or link in the prototype points to /static/uploads/..., /requirements-board or /session-today.

- Learning: each learner and instructor screen shows its learning intent, uses the agreed learner vocabulary, and shows no system terms (for example AGS, LTI, LRS, Tier). Practice and graded work look and read differently. No gamification is added. Roadmap features are absent.

- India context: dates and times show IST. Text in an Indic script renders with the agreed fonts. A throttled (“slow 3G”) run shows loading states, not blank screens.

## 5.4 Lovable pitfalls to watch for

- Unrequested services: Lovable may add login, a database, a cloud service or packages on its own. Reject it (step 5.2.4).

- Renamed routes: Lovable may rename routes or shorten /learn/... paths. Reject it; the backend uses the paths in Appendix A.

- Invented copy: Lovable may invent copy when a label is unclear. Check every label against the documents.

- Colour and font drift: Lovable may change colours or fonts between batches. The Part 0 tokens are the only source; check the tokens file after every batch.

- Silent changes: a push to the synced branch changes the prototype. Compare against the last tag if anything looks different.

## 5.5 Before the prototype is used for connection

- Run a usability round on the accepted prototype, on their own phones: five ITI trainees on the learner screens and two instructors on the instructor screens. The instructional designer runs it. Record what confused them, and route changes through §3.3.

- Have a qualified trade instructor review all trade content in mock data and sample AI output (DEC-26). An unsafe electrical step is a hazard, not a typo. Record the sign-off (VER-35).

## 5.6 Gate

All batches are accepted, tagged and recorded, and the usability round and content review are recorded. A single batch is accepted when its checklist passes and its tag is in the tracker. Signs: senior developer per batch; the instructional designer signs the usability round.

Stop and ask the senior developer if Lovable keeps adding a service you rejected, a batch needs more than its credit budget, or a label in the batch contradicts a signed decision.

# 6. Phase 5 — Connect the accepted design to the backend

Owner: senior developer and front-end developer. Junior developers do template and test work, paired. Output: each screen connected, tested, and recorded as meeting the Definition of Done.

## 6.1 Decision point (DEC-01)

- While DEC-01 stays at its default (design reference; production front end stays server-rendered):

  - Change each existing Jinja template to match the accepted design, extending the app’s existing base template (VER-67: confirm its real name in the repository; Version 2 called it base_shell.html).

  - The routes, guards, handlers and templates already exist. Do not rebuild them.

  - Do not change a handler, guard or template context unless a contract defect is logged and the senior developer has reviewed it.

  - Keep every existing test passing.

  - Lovable’s code is not copied into the repository; it is the reference.

- If DEC-01 is signed for a separate React front end:

  - Build it in its own repository, following the DEC-01 decision record.

  - Before any screen: a JSON API for every page that renders HTML today; a CSRF approach; the cookie strategy inside the Moodle iframe (DEC-22); the LTI launch bootstrap; and a content security policy.

  - Build and test the API layer against the running backend first.

## 6.2 For each screen, in batch order

- Change the template (or build the component) for the screen, keeping the route and guard from Appendix A.

- Run it on local, then staging, with each account that should see it. Check that each account that should not see it gets the access page.

- Compare the screen with the accepted prototype, side by side, using the tagged screenshots.

  - Defects: a different label; a different structure (sections, order, controls); a missing or different state (empty, loading, error, expired session).

  - Not defects: different data values — mock data never equals real data.

- Check the fields against the Phase 3 contract.

  - Defects: a missing, renamed or re-typed field.

  - Additional fields are not defects, but are recorded in the contract.

  - A field the contract says must not be shown, such as an internal ID, appearing on screen is a defect.

- Record the screen in the tracker against the Definition of Done (§6.3).

## 6.3 Definition of Done per screen (DEC-36)

A screen is done only when all ten are true and recorded:

- Its contract row is complete — all columns, including errors and tenant scope — with field names from the code.

- Its mock data was checked against the contract.

- Its Lovable batch is accepted and tagged, with the commit SHA in the tracker.

- The template (or component) is connected. Handler, guard and context are unchanged unless a logged contract defect says otherwise, and existing tests pass.

- Guard tests pass: the allowed role gets the screen, and each refused role gets the access page.

- The cross-tenant and ID-guessing test passes: institute A cannot read institute B’s record by changing an ID.

- The accessibility pass on the connected screen is recorded: keyboard, screen reader, contrast, 375 px width.

- The instructional designer has checked the learning purpose and the learner vocabulary (learner and instructor screens).

- A live check on staging is recorded with evidence (§2.4).

- The tracker row is marked Connected, with links to the evidence.

## 6.4 Gate

Every screen in Appendix C meets the Definition of Done. Signs: senior developer and QA (release gate R1).

Stop and ask the senior developer if making the screen match the design seems to need a change to a handler, guard, query or migration.

# 7. Phase 6 — Live verification

Owner: senior developer and QA. Output: a live verification record in the tracker.

## 7.1 Test plan

| Layer | What it proves | Where | When | Who |
| --- | --- | --- | --- | --- |
| Unit and contract tests | Fields, types and states match the contract (§4.6) | CI | Every change | Developer who changed it |
| Guard and role tests | Each role reaches only its screens; /ops/* refuses without operator sign-in | CI + staging | Every change; each release | Juniors, paired; QA |
| Cross-tenant and ID-guessing (IDOR) | Institute A cannot read B’s attempts, results, receipts, manuals, annotations, analytics or exports by ID | CI + staging | Every change to a data route; each release | Senior developer + QA |
| Course scope | An instructor of one course sees only what DEC-03 allows | Staging | Each release | QA |
| LTI integration | Launch, deep linking, roster sync (NRPS), return to Moodle — across the matrix in §7.2 | Staging Moodle | Each release | QA + senior developer |
| Grade passback (AGS) | A graded score reaches the Moodle gradebook end to end. If not proven, every learner message says plainly that the grade was not sent. | Staging Moodle | Each release | Senior developer |
| Onboarding | /onboard behaves as DEC-02 decided: protected, rate-limited, logged | Staging | Each release | Senior developer |
| Security | CSRF on form and JSON posts; framing limited to registered Moodle origins; malicious EPUB (script inside) is not executed; CSV formula injection neutralised; upload size and type limits; rate limits on /onboard and /ops/login; no secrets in templates or logs | Staging | Each release | Senior developer + QA |
| Exposure re-check | The Phase 1 live checks repeated on the connected build; no /static/uploads/... link on any screen | Staging, then production (approved) | Each release | Senior developer |
| Accessibility | WCAG 2.2 AA on the connected build: keyboard, screen reader, contrast (including tenant accents), focus | Staging | Each release | QA |
| Performance | Page-weight and load-time budgets (to set: assumption — senior developer to correct) on a mid-range Android phone over throttled mobile data; EPUB reader and uploads included | Staging | Each release | Front-end developer |
| Learner loop | On a phone: lesson → quiz → result → hint → My plan → practice → graded retry. At each step: do I know where I am, why I got it wrong, and what to do next? | Staging | Each release | Instructional designer |
| Regression | Full test suite re-run on the connected build; result compared with the Phase 0 baseline | CI + staging | Each release | Senior developer |
| Walkthrough | edvidura_walkthrough.py for all three roles; REPORT.md stored securely | Staging; production under DEC-34 | Each release | Senior developer |

CI: unit, contract, guard and cross-tenant tests run on every change to the repository, and a failing test blocks the merge. Add dependency and secret scanning to the same pipeline.

## 7.2 LTI environment matrix

Test each browser or app in both launch types (inside the Moodle iframe, and in a new window) for each role (learner, instructor, Training Officer).

| Browser or app | Device | Notes |
| --- | --- | --- |
| Chrome | Windows, Android | Third-party-cookie behaviour changes over time; record the version |
| Edge | Windows | — |
| Firefox | Windows | — |
| Safari | macOS | Blocks third-party cookies by default; sessions inside the iframe are most likely to fail here |
| Safari | iOS | As above |
| Moodle app | Android | Launches open in an in-app browser; test the full loop |

Also test a session that expires mid-quiz (VER-38).

## 7.3 Gate

Every test in §7.1 passes, or each failure is recorded with an owner and a date. Signs: senior developer and QA.

# 8. Phase 7 — Release

Owner: product owner and senior developer, with the sign-offs below.

## 8.1 Release gates

| Gate | What must be true | Signs |
| --- | --- | --- |
| R1 Connection complete | Every Appendix C screen meets the Definition of Done (§6.3); every route in §4.4 has a contract row | Senior developer + QA |
| R2 Security and privacy | DEC-02, 03, 09, 19, 21, 22, 24, 28, 29 and 33 signed; VER-07, 08, 09, 36, 37, 45, 46, 59, 60 and 61 recorded; any incident closed. Privacy notice published: what is collected, what instructors and Training Officers can see, how long it is kept, under-18 handling (DEC-19), and where AI requests go (DEC-09) | Senior developer + DPO |
| R3 LTI and grades | DEC-22 signed; VER-02, 03, 20, 24 and 25 recorded; LTI matrix passed; grade passback proven, or every learner message says honestly that grades were not sent | Senior developer + QA |
| R4 Learning | DEC-10, 16, 17 and 26 signed; trade content reviewed (VER-35); learner-loop walk-through recorded; Learning Design Standard version agreed (VER-66); learning-gain baseline captured for the pilot cohort | Instructional designer + product owner |
| R5 Operations and rollout | DEC-35 and DEC-37 signed; production host recorded (VER-65); backup, monitoring, rollback, support and training ready (§8.2) | Product owner + senior developer |

Also confirm before release:

- The test-suite result is recorded: the Phase 0 baseline, re-run after the changes.

- No claim on any screen comes from the dossier, from the audit report’s contradicted items, or from superseded documents.

- No document contains the demo password or any other credential, and the old password no longer works (VER-59).

## 8.2 Rollout plan (DEC-37)

- Back up the production database, and test the restore, before any migration.

- Apply migrations in the order recorded in the repository. Each has a tested rollback.

- Release to one institute, one trade, one cohort first (the pilot). Other institutes follow only after the pilot review.

- Capture the learning-gain baseline — knowledge and practical measures — for the pilot cohort before learners use the platform (DEC-17). If it is missed, it cannot be recovered.

- Turn on monitoring and alerts for: LTI launch failures, grade-passback failures, the learning-record (LRS) outbox backlog, error rates and response times.

- Name the rollback trigger and owner. For example: launch failures above an agreed rate, or any cross-tenant data seen. Roll back to the previous release and restore the backup if needed.

- Publish a support route for institutes: who to contact, and the response times.

- Train the pilot instructors (Train the Trainer) before learners start.

- Tell the pilot institute what changes, when, and what learners will see.

## 8.3 Sign-off

The release is signed in the tracker by the product owner and the senior developer, after QA, the DPO and the instructional designer have signed their gates (R1–R5).

# 9. Phase 8 — Keep it current

- Update the tracker after each step that produces a result: Decision Log, VERIFY Register, Finding Register, Change Log, API Contract, Gate Matrix.

- A status becomes “Verified” only with a recorded result (§2.4).

- When a live check changes a screen, update the features document and the prompt document in the same change, and note it in the Change Log.

- Hold a weekly tracker review, chaired by the senior developer: open decisions, new VERIFY items, gate status, failing tests and incidents.

- Document owners:

| Document | Owner |
| --- | --- |
| Features document | Senior developer |
| Lovable prompt document | Front-end developer |
| Learning Design Standard | Instructional designer |
| Tracker | Senior developer |
| This process | Senior developer |

- Change control (DEC-39). Each batch is built against a named version of the FINAL documents. If a document changes during the build:

  - record the change;

  - list the batches it affects;

  - re-check only those batches against the new version.

- No one edits a FINAL document without a Change Log row.

# 10. Summary of the sequence

| Phase | Output | Gate | Signs |
| --- | --- | --- | --- |
| 0 Baseline | Test results with commit; walkthrough report stored securely; password rotated | VER-01, VER-59, VER-62, VER-65 recorded (part of G-PRE) | Senior developer |
| 1 Live checks | VER-44 to 50, VER-61, 63, 64 results; carried-in checks answered | Recorded; any difference from the documents passed to Phase 2; exposures through §2.3 | Senior developer |
| 2 Decisions | Signed decisions; new prompt-document version | “Before any batch” decisions signed (G-PRE); batch decisions before each batch (Appendix A) | Product owner + senior developer |
| 3 Backend contract | API Contract tab; mocks aligned; contract tests | Each batch’s screens have complete rows before the batch; all Appendix C screens and §4.4 routes before R1 | Senior developer |
| 4 Lovable prototype | Accepted, tagged batches; usability round; content review | Each batch accepted and tagged before the next | Senior developer; instructional designer |
| 5 Backend connection | Screens meeting the Definition of Done | Every screen done (R1) | Senior developer + QA |
| 6 Live verification | Verification record | Every §7.1 test passes, or failures have owners | Senior developer + QA |
| 7 Release | R1–R5 signed; pilot live | All release gates closed | Product owner + senior developer, with QA, DPO and instructional designer (§8.3) |
| 8 Maintenance | Tracker current; weekly review | Every change logged | Senior developer |

# 11. Re-entry rules

| When this is found | Go back to | Update | Who decides |
| --- | --- | --- | --- |
| A contract field is wrong or missing (Phase 4, 5 or 6) | Phase 3 | Contract row → mock module → prompt-document version → re-check affected batches | Senior developer |
| A label differs from Addendum V or the authority section | Phase 2 if it needs a decision; otherwise Phase 4 | Prompt-document version; prototype; template | Product owner (if a decision) |
| A live check contradicts the documents | Phase 2 | Decision; features and prompt documents; affected batches | Product owner + senior developer |
| A security or exposure problem | §2.3 incident path, then Phase 2 | Decision; fix; re-test | Incident lead + DPO |
| The design needs a handler, guard or query change | Phase 3 (contract defect) | Contract; code change under senior review; tests | Senior developer |
| Usability round or learner-loop walk-through shows confusion | Phase 2 (vocabulary or flow) | Prompt-document version; prototype; templates | Product owner + instructional designer |
| A FINAL document changes mid-build | §9 change control | Affected batches only | Senior developer |

# 12. Critical path and parallel lanes

Lane A (senior dev):  Phase 0 ──► Phase 1 live checks ──┐
Lane B (senior dev +                                    ├─► Phase 2 decisions (G-PRE)
        juniors):     Phase 3 contract rows ───────────┘        │
                       (per batch; continues)                    ▼
Lane C (front-end +   Mock alignment (§4.5) ──► Batch 0 ──► S1 … O1 (one at a time)
        designer):                                               │
Lane D (instr. design): usability round + content review ◄──────┤
                                                                 ▼
                       Phase 5 connect (screen by screen, after each batch is accepted)
                                                                 ▼
                       Phase 6 verification ──► Phase 7 release (pilot) ──► Phase 8

- Critical path: Phase 0 → G-PRE decisions → contract and mocks for Batch 0 → Batch 0 → batches in order → connection → verification → release.

- Parallel work:

  - Phase 1 and Phase 3 run together.

  - Contract rows for later batches are written while earlier batches are being built.

  - Connection of a batch’s screens can start once that batch is accepted.

Effort ranges (assumption — senior developer to correct):

| Work | Effort |
| --- | --- |
| Phase 0 | 2–4 days |
| Phase 1 | 3–5 days |
| Phase 2 | 1–2 weeks elapsed (decision meetings) |
| Phase 3 | 1–2 days per batch |
| Phase 4 | 1–3 days per batch |
| Phase 5 | 1–3 days per batch |
| Phase 6 | 1–2 weeks |
| Release preparation | 1 week |

# Appendix A. Gate and Dependency Matrix (summary)

The full matrix, with contract rows and companion-document versions, is in the tracker tab “Gate Matrix”.

| Gate | Screens | Decisions signed | VERIFY recorded | Signs |
| --- | --- | --- | --- | --- |
| G-PRE | All | DEC-01, 27, 08, 16, 32, 35, 39 | VER-01, 51, 52, 58, 59 | Senior developer + product owner |
| Batch 0 | Shell, tokens, shared components | DEC-27, 31, 38, 04, 16 | VER-57, 60 | Senior developer + designer + instructional designer |
| S1 | SH-01, SH-02 | DEC-16, 23 | VER-21 | Front-end + senior developer |
| S2 | SH-03, SH-04, SH-07 | DEC-07 | VER-56, 40 | Front-end + senior developer |
| S3 | SH-05, SH-06 | DEC-02 | VER-24 | Senior developer |
| L1 | LR-01, LR-02 | DEC-28 | VER-33, 41, 55 | Front-end + instructional designer |
| L2 | LR-03, LR-04, LR-06 | DEC-30, 38 | VER-20, 21, 42, 50 | Senior developer + instructional designer |
| L3 | LR-05 | — | VER-38, 31 | Front-end + senior developer |
| L4 | LR-07, LR-08, LR-10 | DEC-09, 10, 18 | VER-14, 15, 29, 43, 48 | Senior developer + instructional designer + DPO |
| L5 | LR-09, LR-11 | DEC-05 | VER-22, 43 | Front-end + instructional designer |
| L6 | LR-12, LR-13 | DEC-24, 30 | VER-21, 42, 49 | Front-end + DPO |
| L7 | LR-14, LR-15 | DEC-28, 06 | VER-10, 12, 15, 45, 55 | Senior developer |
| L8 | LR-16 | DEC-28 | VER-12, 45 | Senior developer |
| T1 | TC-01, TC-02, TC-05 | DEC-03, 26, 28 | VER-10, 13, 26, 33, 56 | Senior developer |
| T2 | TC-03, TC-04, TC-19 | DEC-03, 24 | VER-13, 16, 30 | Front-end + senior developer |
| T3 | TC-06, TC-07, TC-08 | DEC-09, 26 | VER-11, 19, 32 | Senior developer + instructional designer |
| T4 | TC-09, TC-10, TC-11 | DEC-09, 26 | VER-63 | Senior developer + instructional designer |
| T5 | TC-12, TC-13, TC-14 | DEC-18 | VER-43 | Front-end + DPO |
| T6 | TC-15, TC-16 | DEC-05, 26 | VER-11, 33 | Senior developer + instructional designer |
| T7 | TC-17, TC-18 | DEC-03 | VER-05, 06, 44 | Senior developer |
| A1 | SA-01, SA-02, SA-03 | DEC-04, 08 | VER-17 | Front-end + senior developer |
| A2 | SA-04 to SA-07 | DEC-24 | VER-18, 44, 49, 64 | Senior developer + DPO |
| O1 | OP-01, OP-02 | DEC-21, 34 | VER-61 | Senior developer |
| R1 | All screens | DEC-36 | All batch items | Senior developer + QA |
| R2 | — | DEC-02, 03, 09, 19, 21, 22, 24, 28, 29, 33 | VER-07, 08, 09, 36, 37, 45, 46, 59, 60, 61 | Senior developer + DPO |
| R3 | — | DEC-22 | VER-02, 03, 20, 24, 25 | Senior developer + QA |
| R4 | — | DEC-10, 16, 17, 26 | VER-35, 48 | Instructional designer + product owner |
| R5 | — | DEC-35, 37 | VER-65 | Product owner + senior developer |

# Appendix B. Glossary

| Term | Meaning |
| --- | --- |
| AGS | Assignment and Grade Services — the LTI service that sends a score to the Moodle gradebook |
| Addendum V | The section of the FINAL Lovable prompt document that holds the verified labels and banners for the lesson, quiz and Ask Vidura screens. Contents: see the FINAL document |
| Authority section | The part of the FINAL Lovable prompt document that says which source wins when documents disagree. Contents: see the FINAL document |
| Citrus Mint | The design baseline (colours) taken from the code under DEC-27. Hex values: VER-57 |
| CSRF | Cross-site request forgery — a forged form or JSON post; prevented by a token |
| Dossier | The Production Ground-Truth Dossier. Never a source (see the Dossier Verdict) |
| Feedback Assist | Appears to be the instructor tool that drafts feedback on a learner answer (Grade assist, TC-11) — confirm in the FINAL features document. Its output is copied by hand; VER-63 checks that nothing reaches Moodle |
| IDOR | Reading someone else’s record by changing an ID in the URL |
| JWKS | The public keyset Moodle and EdVidura use to check each other’s signed messages |
| LRS | Learning Record Store — receives learning records (xAPI statements) from the outbox |
| LTI 1.3 | The standard that lets Moodle launch EdVidura securely |
| NRPS | Names and Role Provisioning Services — the LTI service for class rosters |
| RLS | Row-level security in PostgreSQL — keeps each institute’s rows separate |
| Stickers | A reward feature considered under DEC-38 and omitted: no gamification |
| Teleport link | A link considered under DEC-38. What it carries and where it goes: VER-60 |
| Time capsule | An instructor download of class data (/teacher/time-capsule.json). Content and scope: VER-61 |
| Training Officer | The UI name for the school-admin role, if DEC-08 adopts it |

For everything else, see the glossary in the Developer Field Guide.