Table of Contents

# EdVidura — Process Review Report

Document reviewed: “EdVidura — Process from Start to Finish: Lovable to Backend”, Version 2, 23 October 2026 (“Replaces the Lovable Build Pack. Use it with the FINAL features and prompt documents.”)

Produced: 23 October 2026, by a run of the EdVidura Process Review Prompt v1 (Loops 1–14).

Companion deliverables:

- EdVidura Process Document Version 3

- Change Table (Version 2 → Version 3)

- Gate and Dependency Matrix

- Tracker additions

- Feedback memo to the author

How to read this report. Section 2 is the one-paragraph answer. Section 3 scores the document. Section 5 lists every finding: High findings come first, each with a plain-English sentence for readers who are not engineers. Section 9 says what to do first. Finding IDs (CON, REF, SEQ, LOV, INT, TST, SEC, LRN, OPS) are review IDs. They do not collide with tracker IDs. New tracker items start at DEC-32 and VER-51.

# 1. Mode and files reviewed

Mode B for the FINAL document family. The process document points to seven companion files. None of them was available to this review:

| File named in Version 2 §0 | Available? | Effect on this review |
| --- | --- | --- |
| EdVidura_Combined_Summary_and_Differences_v2.docx | No | Claims about “which value is correct” are not checked |
| EdVidura_Features_Document_FINAL.docx (Appendices A, C) | No | The 188-route count and screen list are taken on trust; VERIFY |
| EdVidura_Lovable_Prompt_Document_FINAL.docx (authority section, Part 0, Batch 0, Addendum V) | No | Part 0 / Batch 0 order and Addendum V labels are VERIFY |
| EdVidura_Audit_Report_Verification.docx | No | Audit-claim status unknown |
| EdVidura_Enhancement_Tracker_reviewed.xlsx | No | DEC/VER status and numbering unknown; new IDs provisional |
| EdVidura_Package_Review_and_Dossier_Verdict.docx | No | The dossier ban is accepted as stated |
| edvidura_walkthrough.py | No | Script behaviour unknown (VER-62) |

What was available:

- The process document itself. It was read from the .docx, including the title and subtitle stored in the document metadata, which carry the version and date.

- The earlier enhancement package:

  - Features Document v2 and Lovable Prompt Document v3

  - Developer Field Guide and Learning Design & Transformation Standard

  - Decision Log (DEC-01 to DEC-26), VERIFY Register (VER-01 to VER-43), Pedagogy Roadmap (PR-01 to PR-18), and the tracker workbook

- Lovable’s public documentation, read on 23 October 2026: the Git sync overview, project visibility and project Knowledge pages.

What was not done: no repository was read, and no application, test suite or Moodle launch was run. No live probe of any EdVidura environment was made. Every finding that depends on a FINAL file or on live behaviour is marked Mode B — VERIFY and carries a VER number.

New IDs are provisional. DEC-32 to DEC-39 and VER-51 to VER-67 follow on from the numbers this review could see (DEC-31 and VER-50 in Version 2). Before pasting them, check the reviewed tracker for the next free numbers (VER-52 covers this).

Correction. When the review prompt was handed over, the covering message said the seed list held “77 problems, 25 high”. That was wrong. The prompt contained 69 seed findings plus 9 strengths, and 21 of the findings were High. This run confirmed all 69 and added 9 new ones. The confirmed totals are 78 findings (21 High, 43 Medium, 14 Low) and 9 strengths.

# 2. Executive verdict

Version 2 is a good skeleton. The phases are in a sensible order, and one idea stands out: build the backend contract from the code, then shape every Lovable mock from that contract. That is the single best defence against the mismatch errors that usually appear when a prototype is wired to a real backend, and it must be kept.

But a team following Version 2 to the letter could still:

- leave a disclosed password working;

- leave learners’ eBook files publicly reachable while waiting for release;

- connect and release every screen without ever testing that one institute cannot see another institute’s data, that grades reach Moodle, or that the tool works in Safari and the Moodle mobile app;

- start Lovable work under contradictory gates, including a front-end decision (DEC-01) that the document treats as both open and decided;

- release a learning platform without anyone checking, after the prototype stage, that a screen helps a trainee learn.

All of these can be fixed in the document, and Version 3 fixes them on paper. Several fixes still depend on evidence that only the FINAL files and a staging environment can provide.

Rating: Safe after the High fixes.

The three most important problems:

- Secrets and exposures are handled as paperwork, not as incidents (SEC1, SEC2). The demo password is only “removed from the audit report” at release. It must be rotated now. A confirmed public file path is only “recorded”; it must be contained now.

- The tests that matter most are missing (TST1, TST2, TST3, TST6). Nothing tests cross-institute isolation, ID-guessing, grade passback, the LTI browser and device matrix, or the security list.

- The gates contradict each other (CON1, CON2, CON4, SEQ2):

  - DEC-01 is both open and decided.

  - The Phase 2 table, the Phase 2 gate and the summary list different decisions.

  - “Paste as written” conflicts with “choose the vocabulary once”.

  - Nothing aligns the Lovable mocks with the API contract before pasting.

A fourth problem, close behind: learning design is absent after Phase 4 (LRN1, LRN3, LRN5, LRN9). There is no instructional-design role and no learning-purpose check on connected screens. Nothing stops backend codes from leaking into learner text, nothing reviews trade-safety content, and no learning-gain baseline is captured before release.

# 3. Quality scorecard

Scores use the 1–5 rubric in the review prompt §4. “Version 3 (on paper)” means the score the document earns as written. It does not mean the process has been proven in use.

| Dimension | V2 | V3 | Evidence |
| --- | --- | --- | --- |
| Q1 Clarity and structure | 4 | 4 | STR9 (summary table), clear phase headings; OPS7 (compound steps, unexplained terms) |
| Q2 Internal consistency | 2 | 5 | CON1, CON2, CON4, CON5, CON6, CON10 — all resolved in V3 |
| Q3 Reference integrity | 3 | 4 | STR1; REF1–REF6, INT9 fixed; Mode B VERIFYs (VER-51 to VER-54, VER-66) remain |
| Q4 Completeness of scope | 2 | 4 | INT4, INT10, TST1–TST3, TST10, OPS3 added |
| Q5 Sequencing and gates | 3 | 4 | STR3; CON2, SEQ1–SEQ5 → per-batch Gate Matrix, re-entry and change-control rules |
| Q6 Actionability for new graduates | 3 | 4 | STR5; OPS2 (Definition of Done), OPS7, RACI and stop-and-ask lines |
| Q7 Lovable realism | 3 | 4 | STR5; LOV1–LOV9 corrected against Lovable documentation of 23 Oct 2026; VER-58 at build time |
| Q8 Backend integration realism | 3 | 4 | STR4; INT1–INT10 |
| Q9 Verification and testing | 2 | 4 | STR6, STR7; TST1–TST10 → test plan, evidence format, CI |
| Q10 Security, privacy and secrets | 2 | 4 | SEC1, SEC2, SEC7 (High); SEC3–SEC6, SEC8 |
| Q11 Learning design and UX | 1 | 4 | LRN1, LRN3, LRN5, LRN9 (High/Medium); LRN2, LRN4, LRN6–LRN8, LRN10 |
| Q12 Release, operations and maintenance | 2 | 4 | STR8; OPS3, OPS4, OPS5 |
| Q13 Ownership and accountability | 2 | 4 | OPS1, OPS8 → RACI and sign-off per gate |
| Q14 Document control | 3 | 5 | Version and date present; OPS6 → control block, history, audience, purpose |

Version 2 scores 1 or 2 on seven dimensions: Q2, Q4, Q9, Q10, Q11, Q12 and Q13. Q9 and Q10 at 2 do not trigger “Not safe”: that threshold in the rubric is a score of 1. Q11 at 1 is not a rubric trigger either. It is still the dimension furthest from what EdVidura claims to be, and the verdict names it.

Why Version 3 stops at 4. A 5 means the document has been checked against reality: every reference resolves to a current source, every gate has been closed at least once with evidence, and every test in the plan has run. Version 3 has to point at items this review could not close, because the FINAL files and staging environment were not available. Those items are VER-51 to VER-57, VER-59 to VER-66, and the earlier VER-02, 03, 07–10, 13, 20 and 36–38. Q2 and Q14 can reach 5 because they depend only on the text. The others reach 5 after the first full pass through the Gate Matrix with recorded evidence.

# 4. Strengths (keep all nine in Version 3)

| # | Strength | Why it matters |
| --- | --- | --- |
| STR1 | §0 file-authority table with a status per file, and an explicit “Never use” list (dossier, /static/... paths, internal pages, the demo password) | New developers build from one trusted set of sources and know which ones to ignore. Most document drift starts with someone reading the wrong version. |
| STR2 | Phase 0 baseline before anything is built; the historical test counts (265 and 295) must not be quoted until re-run | Turns “Code-present” into something measurable. Without a baseline, no later “it works” means anything. |
| STR3 | Phase 1 live checks come before design decisions, and results that change a screen go to Phase 2 | Design follows what the system really does, not what a document says it does. |
| STR4 | Phase 3 builds the contract from the code — “field names are copied from the code, not from the documents” — and shapes mocks from the contract | The best single defence against integration defects. It is the idea most worth protecting. |
| STR5 | Lovable discipline: no backend, database or authentication in Lovable; one batch at a time; one problem per correction; reject renamed routes and invented copy | Saves credits and keeps the prototype a faithful picture of the real routes. |
| STR6 | Acceptance includes screenshots at 375, 768 and 1280 px, a keyboard pass, a screen-reader spot check and a network-panel check | Accessibility and “no hidden backend” are tested, not assumed. |
| STR7 | Phase 5 tests every screen with an account that should be refused, and treats a label difference from the accepted prototype as a defect | Guards are proven per screen, and visual drift is caught when it is cheap to fix. |
| STR8 | Phase 8: a status becomes “Verified” only with a recorded result; the features and prompt documents change in the same change as the screen | Keeps the documents honest over time. |
| STR9 | A one-table summary of phases, outputs and gates | Lets anyone see the whole process at a glance. Version 3 keeps it and makes it agree with the phases. |

# 5. Findings

All 78 findings, grouped by severity and then by area. Each one says where it goes in Version 3, or which decision or VERIFY item carries it. Version 3 sections are named by their purpose (for example “Version 3 Phase 4 per-batch routine”), so the references stay right if paragraph numbers move.

Evidence tags: [DOC] Version 2 text · [CROSS] comparison inside Version 2 or with the earlier package · [EXTERNAL] Lovable documentation read 23 Oct 2026 · [INFERRED] reasoned risk, also in the VERIFY Register · [STANDARD] named standard · [LEARNING-SCIENCE] named principle · [CALC] computation.

Mode B — VERIFY marks a finding whose final form depends on a FINAL file this review could not open.

## 5.1 High findings (21)

### Correctness and internal consistency

In plain words: the document says the front-end decision is still open in one place and already made in another, so nobody can tell whether Lovable work may start.

CON1 — DEC-01 is presented as both open and decided
Severity: High
Where: §3 Phase 2 table (DEC-01 row); §6 Phase 5 "Decision point";
  §10 summary
What's wrong: Phase 2 lists DEC-01 with the recommendation "Confirm"
  ("…unless the team chooses React"). Phase 5 calls the
  server-rendered route "recommended in the current decision". Phase
  4 is blocked by DEC-01, but the Phase 2 gate and the summary name
  only DEC-27 and DEC-16.
Why it matters: A team can start pasting Lovable batches, or start a
  React repository, without a signed decision.
Fix in Version 3: Phase 2 states DEC-01's status in one place
  (signed, with option, decider and date, or open). DEC-01 is in the
  "before any batch" gate (G-PRE) and in the summary. Phase 5 refers
  to the signed option.
VERIFY: VER-52 (is DEC-01 signed in the reviewed tracker?)
Evidence: [DOC] §3, §6, §10; [CROSS]  — Mode B

In plain words: three parts of the document give three different lists of decisions that must be made before building starts.

CON2 — Gate lists disagree
Severity: High
Where: §3 Phase 2 table "Blocks" column vs §3 gate vs §10 summary
What's wrong: The table says G4 blocks "L2 and Batch 0 shell",
  DEC-31 blocks "any themed screen", DEC-30 blocks L2/L6, DEC-28
  blocks "any screen that shows a file", DEC-01 blocks Phases 4 and
  5. The gate and summary require only DEC-27 and DEC-16 before Part
  0.
Why it matters: Batch 0 (the shell) can be built before G4 is
  decided; themed screens before DEC-31; file screens before DEC-28.
Fix in Version 3: One Gate and Dependency Matrix (per batch) is the
  single source; Phase 2 gate and the summary both point to it and
  agree with it.
Evidence: [DOC] §3, §10; [CROSS]

In plain words: the team is told to paste prompts word for word, but also to choose new screen wording, and nobody is told to update the prompts in between.

CON4 — "Paste as written" conflicts with "choose the vocabulary
  once"
Severity: High
Where: §5.2 step 2; §3 Phase 2 DEC-16 row
What's wrong: Step 2 forbids editing label text. DEC-16 may choose
  display words that differ from the batch text. No step says who
  updates the prompt document, when, or how it is recorded.
Why it matters: Either the developer edits labels ad hoc while
  pasting (untracked drift), or the prototype ships the wrong
  vocabulary.
Fix in Version 3: Phase 2 ends with "apply every signed decision to
  the prompt document as a new version, recorded in the Change Log,
  before any batch is pasted". Phase 4 pastes that version unedited.
Evidence: [DOC] §5.2, §3; [CROSS]

### Sequencing and gates

In plain words: the Lovable sample data was written from documents, and nothing tells anyone to correct it against the real backend before building screens on it.

SEQ2 — No step aligns the Lovable mock-data contract with the API
  contract
Severity: High
Where: §4 Phase 3 → §5 Phase 4
What's wrong: The Lovable prompt document's Batch 0 already defines
  mock modules (written from documents). Phase 3 produces a
  code-derived contract, but no step updates Batch 0 / Part 0 mocks
  to match it before pasting.
Why it matters: This is exactly the divergence Phase 3 warns is "the
  main source of errors" at integration.
Fix in Version 3: Phase 3 ends with a mock-alignment step per batch:
  every mock module's fields, enums and states are checked against
  the contract rows for that batch's screens, and the prompt
  document is updated before pasting. Gate Matrix column "Contract
  rows" enforces it.
Evidence: [DOC] §4, §5; [CROSS] Lovable Prompt Document v3 Batch 0
  mock-data contract

### Lovable realism

In plain words: Lovable’s link to GitHub works in both directions, so anyone who pushes code to the linked branch can silently change a batch that was already approved.

LOV2 — Git sync is two-way; accepted batches can change silently
Severity: High
Where: §5.1 step 1
What's wrong: Version 2 treats GitHub as a one-way record. Lovable's
  Git sync is two-way: commits pushed to the synced branch appear in
  the Lovable project; if histories diverge Lovable pushes to a
  separate lovable-sync branch; force-pushing or rewriting history
  on the synced branch is discouraged.
Why it matters: A push by anyone with access changes the prototype
  that was accepted; nobody is told.
Fix in Version 3: Phase 4 Lovable set-up: protect the synced branch
  (only the Lovable app and the senior developer may push); tag each
  accepted batch; compare against the last accepted tag before each
  batch.
Decision: DEC-32 (Lovable workspace set-up)
Evidence: [EXTERNAL] Lovable docs, Git sync overview, read 23 Oct
  2026

### Backend contract and integration

In plain words: the instructions read as if the screens must be built from scratch, but they already exist and work; following the wording could break working code.

INT1 — The Jinja path is written as greenfield
Severity: High
Where: §6 Phase 5, first bullet and step 1
What's wrong: "Rebuild each accepted batch as a Jinja template…
  Implement the route or the template with the guard." The routes,
  guards and templates already exist.
Why it matters: Invites rewriting working handlers and guards,
  losing behaviour and tests.
Fix in Version 3: Phase 5 Jinja branch: change the existing template
  to match the accepted design; do not change the handler, guard or
  context unless a contract defect is logged and reviewed; existing
  tests must still pass.
Evidence: [DOC] §6; [CROSS] Features Document (templates per screen)

In plain words: the contract records field names but not the things that usually break when a screen is connected — sign-in, security tokens, status values, empty states.

INT2 — The contract lacks the columns that break integrations
Severity: High
Where: §4 Phase 3 field table
What's wrong: Missing: session and authentication (cookie, LTI
  context); CSRF token fields; enumerations and state values (e.g.
  grade_sent, grade_error, ags_available); nullability; limits and
  pagination; time format (UTC stored, IST shown); IDs that must
  never be displayed; upload size and type limits; empty and error
  states; tenant scope.
Why it matters: Mocks that match names but not states produce
  screens that break on null, on an unknown status, or on an empty
  list.
Fix in Version 3: Phase 3 full contract template with those columns
  and three worked examples (a JSON endpoint, a server-rendered
  page, a form post).
Evidence: [DOC] §4; [CROSS] Features Document §3.B, §3.L

In plain words: the contract covers screens, but the Moodle sign-in, grade sending and export routes have no screen, so they are never written down or checked.

INT4 — Routes without screens are outside the contract
Severity: High
Where: §4 Phase 3 gate ("every screen in Appendix C has a contract
  row")
What's wrong: Integration also depends on LTI login, launch, JWKS,
  deep-link return, AGS, NRPS, return-to-Moodle, CSV/JSON exports,
  receipt JSON, time-capsule JSON, ops retry and platform
  activation.
Why it matters: The routes most likely to fail in a real Moodle are
  not in the contract and not in any gate.
Fix in Version 3: Phase 3 adds a "Routes without screens" contract
  section; release gate R3 (LTI and grades) requires it.
Evidence: [DOC] §4; [CROSS] Features Document §3.A, §3.L, §3.M

In plain words: removing the public /static folder to protect uploaded files could also remove the app’s own stylesheets and scripts.

INT6 — DEC-28 "remove the /static mount" may break the app's own
  assets
Severity: High
Where: §3 DEC-28 row; §0 "Never use"; §5.3 last bullet; §7 step 5
What's wrong: The exposure is tenant uploads (extracted EPUBs under
  /static/uploads/epub/). CSS, JS and fonts are usually also under
  /static. "Never use any /static/... path" bans the app's own
  stylesheet.
Why it matters: Removing the mount as written breaks every page's
  styling; the ban makes the live check in Phase 6 fail on every
  screen.
Fix in Version 3: Split public build assets from tenant uploads;
  only uploads move behind authenticated, tenant-scoped routes.
  "Never use" bans /static/uploads/... and any tenant file path, not
  build assets.
VERIFY: VER-55 (what /static serves) — Mode B
Evidence: [DOC] §0, §3, §5.3, §7; [INFERRED]

### Verification and testing

In plain words: nothing in the process checks that one institute cannot see another institute’s learners and results.

TST1 — No cross-tenant or ID-guessing test anywhere
Severity: High
Where: §7 Phase 6 step 3; §6 Phase 5 step 2
What's wrong: Tests cover role (learner vs teacher vs admin) only —
  never institute A vs institute B, never guessing another record's
  ID on /quiz/result/{attempt_id}, receipts, manuals or the
  annotations API, never course scope (DEC-03).
Why it matters: Cross-tenant leakage is the platform's largest risk.
Fix in Version 3: Definition of Done item 6 and the Phase 6 test
  plan: two demo institutes on staging; per screen, request B's
  record by ID while signed in to A; expect the access page.
Evidence: [DOC] §6, §7; [STANDARD] OWASP ASVS access control

In plain words: the process never checks that a quiz score actually reaches the Moodle gradebook, although this has failed before.

TST2 — Grade passback is never verified
Severity: High
Where: §7 Phase 6; §8 Phase 7
What's wrong: No step checks AGS end to end, despite the known
  Moodle token.php / null-JWKS failure.
Why it matters: Learners and instructors may believe grades are in
  Moodle when they are not.
Fix in Version 3: Phase 6 AGS end-to-end check on staging Moodle;
  release gate R3: either proven, or every learner message confirmed
  to say honestly that grades were not sent.
Evidence: [DOC] §7, §8; [CROSS] Features Document §3.L (VER-20)

In plain words: the tool runs inside Moodle, and nothing tests it in Safari, on iPhones or in the Moodle phone app, where it is most likely to break.

TST3 — No LTI environment matrix
Severity: High
Where: §7 Phase 6
What's wrong: No test across browsers (Safari macOS and iOS),
  third-party cookies in the Moodle iframe, the Moodle mobile app on
  Android, deep linking, or session expiry mid-quiz (VER-38).
Why it matters: Launch and session failures appear only in these
  environments; most Indian learners use Android phones.
Fix in Version 3: Phase 6 LTI matrix: browser × launch type (iframe
  / new window / mobile app) × role.
Evidence: [DOC] §7; [STANDARD] LTI 1.3; [CROSS] DEC-22

In plain words: there is no list of security tests, so common attacks (forged form posts, poisoned files, spreadsheet formulas) are never checked.

TST6 — No security test list
Severity: High
Where: §7 Phase 6; §8 Phase 7
What's wrong: No CSRF test; no framing (frame-ancestors) test; no
  malicious EPUB; no CSV formula injection; no upload limits; no
  rate limiting on /onboard or /ops/login; no
  secrets-in-templates/logs check.
Why it matters: Each is a known risk in this stack (Features
  Document, Field Guide) with no step that tests it.
Fix in Version 3: Phase 6 security test list; release gate R2.
Evidence: [DOC] §7; [STANDARD] OWASP ASVS; [CROSS] VER-10, VER-13,
  VER-36, VER-37

### Security, privacy and secrets

In plain words: a password was written into a document; deleting the text does not stop the password working — it has to be changed.

SEC1 — Disclosed demo password is not rotated
Severity: High
Where: §8 Phase 7 ("The demo password is removed from the audit
  report")
What's wrong: Removal from text does not revoke a credential, and it
  is left until release.
Why it matters: Anyone who saw the audit report can sign in until
  the password changes.
Fix in Version 3: Phase 0: rotate the password now; search git
  history, shared drives and chat for copies; confirm environments
  do not share credentials.
VERIFY: VER-59
Evidence: [DOC] §0, §8

In plain words: if the live checks find learners’ files open to the public, the process only writes it down and waits; it should be fixed straight away.

SEC2 — Live exposure checks have no incident path
Severity: High
Where: §2 Phase 1 rows VER-45 (unauthenticated eBook files) and
  VER-46 (internal pages reachable logged out); §3 DEC-28
What's wrong: A "Confirmed" result is recorded and passed to Phase 2
  and release. Learner content would stay exposed meanwhile.
Why it matters: An active exposure of learner content on production;
  a possible personal-data breach under the DPDP Act 2023.
Fix in Version 3: Phase 1 incident path: contain immediately → DPO
  assesses personal-data impact → notify as the DPO decides → fix →
  re-test → record.
Decision: DEC-33 (incident lead and response)
Evidence: [DOC] §2; [STANDARD] DPDP Act 2023

In plain words: the release checklist leaves out India’s data-protection requirements — what learners are told, what teachers can see, and how under-18 trainees are handled.

SEC7 — DPDP items absent from the release gate
Severity: High
Where: §8 Phase 7
What's wrong: No privacy notice, no instructor-visibility statement,
  no under-18 handling (DEC-19), no retention (DEC-24), no AI data
  flows (DEC-09).
Why it matters: Some ITI trainees are under 18; release without
  these is a legal and trust risk.
Fix in Version 3: Release gate R2 (security and privacy) lists them;
  DPO signs.
VERIFY: VER-53 (are DEC-09, DEC-19 closed?) — Mode B
Evidence: [DOC] §8; [STANDARD] DPDP Act 2023

### Learning design, UX and India context

In plain words: after the prototype stage, nobody checks that a connected screen still helps a trainee learn.

LRN1 — The process never checks learning design
Severity: High
Where: Whole document; only trace is §5.3 "Batch 0's common
  checklist (items 1 to 19)"
What's wrong: No instructional-design role; no learning-purpose
  check when screens are connected or released; the Learning Design
  & Transformation Standard is not in §0.
Why it matters: EdVidura's claim is better learning. A process that
  checks security and layout but not learning cannot deliver that
  claim.
Fix in Version 3: Instructional designer in the RACI; learning
  checks in Phase 2 (decisions), Phase 4 (learning intent), Phase 5
  (Definition of Done item 8), Phase 6 (learner-loop walk-through on
  a phone), Phase 7 (baseline, release gate R4).
VERIFY: VER-66 (status of the Standard vs FINAL)
Evidence: [DOC]; [LEARNING-SCIENCE] constructive alignment

In plain words: if the team shows learners whatever the backend sends, codes like “AGS off” will reach the screen.

LRN3 — DEC-16 "use code values for everything the backend sends"
Severity: High
Where: §3 Phase 2, DEC-16 row
What's wrong: Read literally, backend enum values become learner
  text.
Why it matters: Learners see jargon ("AGS off") instead of plain
  words — the problem the earlier vocabulary work fixed.
Fix in Version 3: Code values stay in data; a display-mapping layer
  (the strings file) turns each value into the agreed learner words.
Evidence: [DOC] §3; [CROSS] Features Document v2 §5.1

In plain words: sample electrical content is never checked by a qualified electrician, and a wrong safety step is dangerous, not just a typo.

LRN5 — No trade-content safety review
Severity: High
Where: §5 Phase 4; §8 Phase 7
What's wrong: Mock and AI-generated electrical content is never
  reviewed by a qualified trade instructor.
Why it matters: Demo audiences and learners may see unsafe
  procedures.
Fix in Version 3: Phase 4 trade-content review of mock content
  before demos; release gate R4 (DEC-26, VER-35).
Evidence: [DOC]; [CROSS] DEC-26

### Ownership, release and operations

In plain words: there is no single checklist that says when one screen is finished, so two people could disagree.

OPS2 — No Definition of Done per screen
Severity: High
Where: Scattered across §4–§7
What's wrong: Pieces of "done" are in four phases; none is complete.
Why it matters: Screens are marked connected with different
  evidence; gaps (isolation, accessibility, learning) slip through.
Fix in Version 3: Phase 5 Definition of Done (§6.3), 10 points.
Decision: DEC-36
Evidence: [DOC] §4–§7

In plain words: the release step has no plan for rolling out to one institute first, watching for problems, or undoing the release if it goes wrong.

OPS3 — Release has no rollout, rollback or operations plan
Severity: High
Where: §8 Phase 7
What's wrong: No environments, backup before migration, migration
  order, staged rollout, monitoring and alerts, rollback, support
  route, instructor training or communication.
Why it matters: A failed release at an institute has no safe way
  back.
Fix in Version 3: Phase 7 release section; release gate R5.
Decision: DEC-37 (rollout and rollback)
Evidence: [DOC] §8

## 5.2 Medium findings (43)

### Correctness and internal consistency (5)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| CON3 | §5.1 step 3 vs §5.2 | §5.1 says paste Part 0 and nothing else “until Part 0 has produced a working shell”; §5.2 lists “Batch 0, then S1…”. In the Lovable document lineage, Batch 0 builds the shell. [CROSS] Mode B | Version 3 Phase 4 states one order consistent with the FINAL document; VER-51 |
| CON5 | §2 Phase 1 gate | Only “Confirmed” results that change a screen go to Phase 2. A “Disproved” result (e.g. live labels differ from Addendum V, VER-48) also changes a screen. [DOC] | Version 3 Phase 1 gate: “any result that differs from the documents” |
| CON6 | §6 Phase 5 steps 3–4 | “Any unexpected field is a defect” fails harmless additions; “a difference in label or data is a defect” fails every screen, because mock data never equals live data. [DOC] | Version 3 Phase 5 defect rule: missing, renamed or re-typed fields; label differences; structure or state differences |
| CON8 | §4 Phase 3 “Errors” field | Assumes JSON status codes; the server-rendered app returns access.html from many routes. [CROSS] Mode B | Version 3 Phase 3 records real status code and template per error; VER-56 |
| CON10 | §3 DEC-16 row | Conflates DEC-08 (UI terminology: Institute, Training Officer) with DEC-16 (one learner vocabulary), and names one option “the senior’s”, personalising a product decision. [CROSS] | Version 3 Phase 2 lists DEC-08 and DEC-16 separately, with neutral options |

### Reference integrity (4)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| REF1 | §2, §3, §8 | Mixed identifier schemes: DEC-nn, VER-nn, “G4”, “audit claim 6/7/8/23”. Audit claims and G4 are not tracker rows and are not in the Phase 1 gate or release list. [DOC] | Audit claim 6 → VER-63; 7 → VER-61; 8 → VER-64; 23 → VER-65; G4 → DEC-38 |
| REF2 | §0 | The Learning Design & Transformation Standard, Developer Field Guide and Decision/VERIFY/Change Logs have no status. [CROSS] Mode B | Version 3 §0 lists them with a status; VER-66 |
| REF3 | Whole document | Only VER-01 and VER-44 to VER-50 appear. Earlier items that block safe integration have no phase: VER-02/03 (roles), VER-07 to 09 (RLS), VER-10 (EPUB), VER-13 (CSV), VER-20 (AGS), VER-36 (CSRF), VER-37 (framing), VER-38 (session expiry). [CROSS] Mode B | Version 3 Phase 1 carries them, or states FINAL closed them; Gate Matrix places each; VER-54 |
| REF4 | §3 Phase 2 | DEC-02, 03, 09, 10, 19, 21, 22 block safe release but are not listed. [CROSS] Mode B | Version 3 Phase 2 complete decision list grouped by what each blocks; VER-53 |

### Sequencing and gates (4)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| SEQ1 | §10 and every gate | Fully serial: Phase 4 waits for every contract row; Phase 1 and Phase 3 could run in parallel. [DOC] | Version 3 per-batch Gate Matrix and critical path with parallel lanes |
| SEQ3 | Phases 5–6 | No re-entry rule when a later phase finds an earlier output wrong. [DOC] | Version 3 re-entry rules (which phase, what is updated, who decides) |
| SEQ4 | Whole document | No critical path, durations or milestones. [DOC] | Version 3 critical path with effort ranges as assumptions |
| SEQ5 | Phases 4–5 | No rule for a FINAL document changing mid-build. [DOC] | DEC-39 (freeze per batch, re-baseline affected batches) |

### Lovable realism (6)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| LOV1 | §5.2 step 5 | “Commit with the batch ID in the message” isn’t how Lovable’s Git sync works. Lovable commits and pushes through its GitHub app, attributed to the member; its documentation describes no per-change message. [EXTERNAL] | Version 3 Phase 4: git tag per accepted batch (e.g. batch-S1-accepted), SHA in tracker |
| LOV3 | §5.1 | Project access not stated. Workspace access is the default; Restricted (invited users only) is a Business/Enterprise feature; a separate public-remix setting lets anyone with the link preview and copy the project. [EXTERNAL] | DEC-32; Version 3 Phase 4 set-up names plan, access level, “public remixing off” |
| LOV4 | §5.1 step 3 | Hard rules pasted once drift over long sessions; Lovable supports persistent project-level instructions (Knowledge). [EXTERNAL] | Version 3 Phase 4: Part 0 hard rules in project Knowledge; VER-58 |
| LOV5 | §5.3 network check | “No requests during mock flows” will fail on the preview’s own scripts, hot reload and assets. [INFERRED] | Version 3: no request to any API, authentication, database or third-party data host; own static assets and self-hosted fonts allowed |
| LOV6 | §5.4 | Dependency drift unchecked: Lovable may add packages or environment files unasked. [INFERRED] | Version 3 per-batch routine: diff package.json, .env*, supabase/ against last accepted tag |
| LOV7 | §5.2 step 4 | No credit stop rule. [DOC] | Version 3: after two failed corrections, revert to last accepted tag and re-prompt smaller; credit budget per batch (DEC-32) |

### Backend contract and integration (4)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| INT3 | §4 field table | Server-rendered screens have no “response JSON”; their contract is the template context plus form field names. [CROSS] | Version 3 Phase 3 says so, with a worked example (LR-06) |
| INT5 | §6 React branch | Understates the work: most pages have no JSON endpoint; React also needs CSRF, iframe cookie strategy (DEC-22), LTI bootstrap and CSP. [CROSS] | Version 3 Phase 5 React branch points to the DEC-01 record and lists the blockers |
| INT7 | §4, §5 | Manual contract checks will not survive change. [INFERRED] | Version 3: mock types generated from, or checked against, the contract; schema tests in CI |
| INT10 | §4 endpoint list | /quiz/result/{attempt_id}/receipt.json and /teacher/time-capsule.json are data exports with no screen, no privacy review and no learner-wording rule (“Download receipt file”, not JSON). [CROSS] | Version 3 Phase 3 routes-without-screens section with personal-data note; VER-61 |

### Verification and testing (6)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| TST4 | §5.3 only | Accessibility tested on the prototype only, not on the connected build. [DOC] | Definition of Done item 7; Version 3 Phase 6 WCAG 2.2 AA pass, including themed tenant pages |
| TST5 | Phase 6 | No performance or low-bandwidth test for mid-range Android on mobile data. [INFERRED] | Version 3 Phase 6 page-weight and load budgets; throttled EPUB and upload tests |
| TST7 | Phases 1, 6 | No evidence format. [DOC] | Version 3 evidence format: environment, commit, role, time, result, screenshot or HTTP log |
| TST8 | Phases 0, 7 | Test suite run at baseline and release only; no CI. [DOC] | Version 3: contract and guard tests in CI on every change; new templates need tests |
| TST9 | §1 step 4 | Walkthrough script run with real credentials, without review; credential source and target tenant unstated. [DOC] | Version 3 Phase 0: review script first; credentials from a secrets manager; demo tenant only; VER-62; DEC-35 |
| TST10 | §7 Phase 6 | Omits NRPS roster sync, deep linking, a test-suite re-run on the connected build, and any /onboard test. [DOC] | Version 3 Phase 6 test plan; release gate R3 |

### Security, privacy and secrets (5)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| SEC3 | §2 Phase 1 | Probing production (including unauthenticated requests) without stated authorisation or logging; the designer gets live access. [DOC] | DEC-34; Version 3 §0A environments and probe rules |
| SEC4 | §3 DEC-29 | “Decide per table” gives no criteria for institutions and lti_platforms (registration data). [DOC] | Version 3 Phase 2 criteria: what reads them before tenant resolution, who must never see other rows, which test proves it |
| SEC5 | §3 G4; §2 audit claim 7 | Teleport link, report-a-problem and time-capsule export have no security or privacy step. [DOC] | DEC-38; VER-60; VER-61 |
| SEC6 | Whole document | No threat model, dependency or secret scanning, or static analysis. [DOC] | Version 3 Phase 6/CI hygiene list |
| SEC8 | §1 step 4 | Walkthrough REPORT.md and live screenshots may hold learner personal data; storage unstated. [DOC] | Version 3 Phase 0: store in an access-controlled location, not in documents or chat |

### Learning design, UX and India context (6)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| LRN2 | §3 DEC-30 | 60% as a constant is acceptable now, but competence thresholds belong to the course or skill, and learners should see where 60% comes from. [LEARNING-SCIENCE] valid assessment | Version 3 Phase 2 note; configurable threshold to the Pedagogy Roadmap |
| LRN4 | Phase 4 → 5 | No usability round with real users before connection. [INFERRED] | Version 3 Phase 4: five ITI trainees on their own phones and two instructors walk the accepted prototype |
| LRN6 | §3 DEC-27, DEC-31 | Citrus Mint and tenant accents: light mint and citrus hues often fail 4.5:1 with white text; “six hues” undefined. [CALC] required. Mode B | Version 3 Phase 2 computation and thresholds (white on accent and accent text ≥ 4.5:1; focus and control boundary ≥ 3:1); VER-57 |
| LRN7 | §5.3, §7 | IST display, Indic scripts and slow-network states are not in any acceptance or live check. [DOC] | Version 3 Phase 4 and Phase 6 checks |
| LRN9 | §8 Phase 7 | No learning-gain baseline before learners use the platform (DEC-17). [CROSS] | Version 3 Phase 7; DEC-37; release gate R4 |
| LRN10 | §2 Phase 1 “Top Learners” | If it exists it is a ranking of learners — a leaderboard, banned by the Learning Design Standard (principle 12, ethical analytics). Version 2 leaves it an open choice. [LEARNING-SCIENCE] | Version 3 Phase 2: remove unless the product owner records a reason; VER-64 |

### Ownership, release and operations (3)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| OPS1 | Every phase | Owners are roles only; junior developers are invisible; no RACI. [DOC] | Version 3 §0B RACI with sign-off per gate |
| OPS4 | §1, §2, §7 | “Local”, “the Moodle deployment”, “the live deployment” and “production” used loosely; environments undefined. [DOC] | DEC-35; Version 3 §0A Environments |
| OPS8 | §8 Phase 7 | Release signed by product owner and senior developer only; no QA, security/DPO or instructional-design sign-off. [DOC] | Version 3 release gates R1–R5 each with named signers |

## 5.3 Low findings (14)

| ID | Where | What’s wrong | Fix / Decision / VERIFY |
| --- | --- | --- | --- |
| CON7 | §4 heading | “The most important step for ‘no errors’” over-claims; integration defects also come from auth, cookies, CSRF, tenancy, timing. [DOC] | Version 3 heading: the main defence against data-shape defects |
| CON9 | §2 owner line | The designer joins live visual checks; environment and accounts not stated. [DOC] | DEC-34; designers use staging |
| CON11 | §2 row “standalone banner” | “Standalone banner” undefined; tracker column says “Dossier claim” although the dossier is a never-use source. [DOC] | Version 3 Phase 1 states what is checked and why |
| CON12 | §6 Phase 5 | Names base_shell.html as the base template; not named in earlier documents. [CROSS] | Version 3: “the app’s base template (VER-67)” |
| REF5 | §0, §3, §2 | “Authority section”, “Addendum V”, “Citrus Mint”, “teleport link”, “time capsule”, “Feedback Assist”, “stickers” unexplained. [DOC] | Version 3 glossary with one-line glosses |
| REF6 | §0 | File names carry no versions or dates; “FINAL” and “_reviewed” are not versions. [DOC] | Version 3 §0: version, date, owner per file |
| LOV8 | §5 | Visual edits and drafts bypass the prompt record. [EXTERNAL] | Version 3 Phase 4: ban, or log as prompt changes |
| LOV9 | §5.3 | Three widths × every screen and state × 22 batches is hundreds of manual screenshots. [CALC] | Version 3: Playwright screenshot script against the synced repository’s local build |
| INT8 | §4 “Mock file” | “Chosen by the team” invites file sprawl. [DOC] | Version 3: one module per entity, as in the mock-data contract |
| INT9 | §4 endpoint list | Heading says “JSON endpoints” but lists /teacher/analytics.csv and /teacher/attempts.csv. [DOC] | Version 3 splits JSON endpoints and file exports |
| LRN8 | §3 G4 | Omitting stickers is right; the reason isn’t recorded. [LEARNING-SCIENCE] | DEC-38 records the reason (no gamification, principle 12) |
| OPS5 | §9 Phase 8 | No cadence or owner for tracker upkeep. [DOC] | Version 3 Phase 8: weekly review chaired by the senior developer; owner per document |
| OPS6 | Title block | Version and date present; no owner, approver, audience, purpose or summary of changes. [DOC] | Version 3 document control block |
| OPS7 | Whole document | No glossary pointer; some steps combine several actions. [DOC] | Version 3: split steps, stop-and-ask lines, glossary |

## 5.4 Count check

| Area | High | Medium | Low | Total |
| --- | --- | --- | --- | --- |
| CON Correctness | 3 | 5 | 4 | 12 |
| REF References | 0 | 4 | 2 | 6 |
| SEQ Sequencing | 1 | 4 | 0 | 5 |
| LOV Lovable | 1 | 6 | 2 | 9 |
| INT Integration | 4 | 4 | 2 | 10 |
| TST Testing | 4 | 6 | 0 | 10 |
| SEC Security | 3 | 5 | 0 | 8 |
| LRN Learning | 3 | 6 | 1 | 10 |
| OPS Operations | 2 | 3 | 3 | 8 |
| Total | 21 | 43 | 14 | 78 |

# 6. Phase-by-phase analysis

Each block covers:

- Purpose: what the phase is for.

- Works: what is good and should be kept.

- Wrong or missing: the problems, with finding IDs.

- New-graduate test: could a first-month developer run the phase from the text alone?

- Version 3 changes: what the improved document does differently.

### §0 Which files to use

- Purpose: one authority list.

- Works: STR1, the status column and the “Never use” list.

- Wrong or missing:

  - no versions or owners (REF6);

  - the Standard and Field Guide are missing (REF2);

  - the /static ban is too broad (INT6);

  - no environments or roles (OPS4, OPS1).

- New-graduate test: passes for “which file”, fails for “which version” and “where do I run this”.

- Version 3 changes: versions, dates and owners per file; Standard and Field Guide status; corrected “Never use” list; new §0A Environments, accounts and access; new §0B Roles and RACI.

### Phase 0 — Baseline

- Purpose: prove the code runs before anything is built.

- Works: STR2; recording passed, failed and skipped counts with the date.

- Wrong or missing:

  - the disclosed password is not rotated (SEC1);

  - the walkthrough script runs unreviewed with real credentials (TST9), and its outputs may hold personal data (SEC8);

  - environment and commit are not recorded (TST7);

  - “the Moodle deployment” is undefined (OPS4).

- New-graduate test: fails on “which deployment” and “where do I get the passwords”.

- Version 3 changes: rotate the password and search for copies; review the script; take credentials from a secrets manager; run on a demo tenant; record environment and commit with the baseline.

### Phase 1 — Live checks

- Purpose: let reality change the design before it is built.

- Works: STR3; each check has an account, a reason and a tracker link.

- Wrong or missing:

  - no incident path for confirmed exposures (SEC2);

  - no authorisation for probes (SEC3);

  - incomplete gate logic (CON5);

  - audit claims are not tracker rows (REF1);

  - earlier blocking VERIFY items are absent (REF3);

  - “standalone banner” is undefined (CON11);

  - “Top Learners” is left open (LRN10);

  - no evidence format (TST7).

- New-graduate test: fails on “what do I do if the eBook files are public”.

- Version 3 changes: incident path (DEC-33); probe rules (DEC-34); gate on “any difference”; audit claims mapped to VER-61, 63, 64, 65; earlier VERIFY items carried in; evidence format.

### Phase 2 — Decisions

- Purpose: sign the choices that shape the screens.

- Works: each decision has a recommendation and a “Blocks” column.

- Wrong or missing:

  - DEC-01 is both open and decided (CON1);

  - gate lists disagree (CON2);

  - no step applies signed decisions to the prompt document (CON4);

  - DEC-08 and DEC-16 are conflated (CON10);

  - backend codes may reach learner text (LRN3);

  - DEC-28 is too broad (INT6);

  - no criteria for DEC-29 (SEC4);

  - blocking decisions are missing (REF4);

  - no instructional-design reviewer (LRN1);

  - contrast is not computed (LRN6);

  - G4 is not a decision row (REF1).

- New-graduate test: fails — a junior cannot tell which decisions block their batch.

- Version 3 changes: complete list grouped by what each decision blocks; DEC-01 stated once; display mapping; assets/uploads split; DEC-29 criteria; G4 → DEC-38; “apply decisions to the prompt document as a new version” step; instructional designer on learning decisions; contrast computation (VER-57).

### Phase 3 — Backend contract

- Purpose: shape every mock from the real code.

- Works: STR4, the strongest idea in the document.

- Wrong or missing:

  - columns that break integrations (INT2);

  - server-rendered context (INT3);

  - routes without screens (INT4);

  - mock alignment (SEQ2);

  - automation (INT7);

  - naming (INT8);

  - CSV listed as JSON (INT9);

  - exports unreviewed (INT10);

  - error behaviour (CON8);

  - the over-claiming heading (CON7).

- New-graduate test: partly passes. A junior can fill a row, but would invent JSON for a template page.

- Version 3 changes: full template with three worked examples; routes-without-screens section; mock-alignment step per batch; generated or checked mock types; naming rule.

### Phase 4 — Lovable prototype

- Purpose: an accepted visual reference per batch.

- Works: STR5, STR6; the rejection of Lovable-added backends.

- Wrong or missing:

  - Git sync realities (LOV1, LOV2);

  - access (LOV3);

  - persistent rules (LOV4);

  - a network check that fails falsely (LOV5);

  - dependency drift (LOV6);

  - credit stop rule (LOV7);

  - visual edits (LOV8);

  - screenshot load (LOV9);

  - Part 0 / Batch 0 order (CON3);

  - learning intent (LRN1);

  - IST and Indic (LRN7);

  - usability (LRN4);

  - trade content (LRN5).

- New-graduate test: passes for pasting; fails for “how do I know nobody changed my accepted batch”.

- Version 3 changes: corrected set-up (DEC-32), and a per-batch routine:

  - Tag the last accepted state.

  - Paste the batch.

  - Diff dependencies against the last accepted tag.

  - Run the checklist and the screenshot script.

  - Allow at most two corrections, then revert.

  - Tag as accepted and record the SHA.

- Plus a learning-intent check and a usability round.

### Phase 5 — Backend connection

- Purpose: connect the accepted design to the real backend.

- Works: STR7, the denied-account check and side-by-side comparison.

- Wrong or missing:

  - written as greenfield (INT1);

  - React branch understated (INT5);

  - defect rules (CON6);

  - no Definition of Done (OPS2);

  - base template name assumed (CON12).

- New-graduate test: fails dangerously — “implement the route” could lead a junior to rewrite a working handler.

- Version 3 changes: modify existing templates and keep handlers and guards; React branch points to the DEC-01 record; corrected defect rule; 10-point Definition of Done (DEC-36).

### Phase 6 — Live verification

- Purpose: prove the connected build works.

- Works: walkthrough re-run; Phase 1 checks repeated on the build; wrong-account guard tests; JSON endpoints checked live.

- Wrong or missing:

  - no cross-tenant tests (TST1);

  - no AGS check (TST2);

  - no LTI matrix (TST3);

  - accessibility not checked on the build (TST4);

  - no performance test (TST5);

  - no security tests (TST6);

  - no evidence format (TST7);

  - no CI (TST8);

  - NRPS, deep link and /onboard missing (TST10);

  - no learner-loop walk-through (LRN1).

- New-graduate test: fails — the most important tests are not named.

- Version 3 changes: a risk-based test plan by layer, environment, timing and owner; release gates R1–R4.

### Phase 7 — Release

- Purpose: sign off.

- Works: decisions and evidence are required; the dossier and superseded claims are excluded.

- Wrong or missing:

  - password handled too late (SEC1);

  - no DPDP items (SEC7);

  - no operations plan (OPS3);

  - narrow sign-off (OPS8);

  - no learning baseline (LRN9);

  - no AGS position (TST2).

- New-graduate test: not applicable (senior task), but the senior would miss rollback and monitoring.

- Version 3 changes: release gates R1–R5; staged pilot (DEC-37); backup, migration, monitoring, rollback, support, training and communication; baseline captured before learners start.

### Phase 8 — Keep it current

- Purpose: keep documents and tracker true.

- Works: STR8.

- Wrong or missing: no cadence or owner (OPS5); no change control (SEQ5).

- New-graduate test: fails on “who updates this, and when”.

- Version 3 changes: weekly tracker review; an owner per document; freeze-per-batch rule (DEC-39).

### §10 Summary

- Works: STR9.

- Wrong: its gates disagree with Phase 2 (CON2).

- Version 3 changes: the summary gates are copied from the Gate Matrix, so they agree.

# 7. Reference and consistency tables

## 7.1 Reference resolution (Loop 2)

| Reference in Version 2 | Resolves? | Source | Matches what Version 2 assumes? | Finding |
| --- | --- | --- | --- | --- |
| Combined Summary and Differences v2 | Not checked | FINAL family (not available) | VERIFY | REF6, VER-53 |
| Features Document FINAL, Appendix A “188 routes” | Not checked | FINAL family | VERIFY; the earlier Features Document listed 49 routes on screens, so 188 is plausible for a full inventory | INT4 |
| Features Document FINAL, Appendix C screens | Partly | Earlier Features Document v2 (51 screens) | Likely the same 51 screens; VERIFY | — |
| Lovable FINAL Part 0 / Batch 0 | Partly | Lovable Prompt Document v3 (Batch 0 builds the shell) | No — §5.1 implies Part 0 builds the shell | CON3, VER-51 |
| Batch 0 common checklist items 1–19 | Yes | Lovable Prompt Document v3 (19 items, 6 learning checks) | Yes, if FINAL kept them | LRN1 |
| Authority section; Addendum V | Not checked | FINAL family | VERIFY | REF5 |
| Enhancement Tracker “_reviewed” | Not checked | Earlier tracker (DEC-01–26, VER-01–43) | Numbering continues (DEC-27–31, VER-44–50) | REF6, VER-52 |
| VER-01 | Yes | Earlier VERIFY Register | Yes (baseline) | — |
| VER-44 to VER-50 | Not checked | Reviewed tracker | VERIFY | VER-52 |
| DEC-01 | Yes | Earlier Decision Log | Status unclear (open vs decided) | CON1, VER-52 |
| DEC-16 | Yes | Earlier Decision Log (one learner vocabulary) | No — Version 2 merges it with DEC-08 terminology | CON10 |
| DEC-27 to DEC-31 | Not checked | Reviewed tracker | VERIFY | VER-52 |
| “G4” | No | No tracker row seen | — | REF1 → DEC-38 |
| Audit claims 6, 7, 8, 23 | No | Audit Report Verification (not available) | — | REF1 → VER-63, 61, 64, 65 |
| Earlier blocking items VER-02/03, 07–10, 13, 20, 36–38 | Yes | Earlier VERIFY Register | Not mentioned in Version 2 | REF3, VER-54 |
| Earlier blocking decisions DEC-02, 03, 09, 10, 19, 21, 22 | Yes | Earlier Decision Log | Not mentioned in Version 2 | REF4, VER-53 |
| Learning Design Standard; Developer Field Guide | Yes | Earlier package | Not listed in §0 | REF2, VER-66 |
| base_shell.html | Not checked | Not in earlier documents | VERIFY | CON12 |
| edvidura_walkthrough.py | Not checked | Not available | VERIFY | TST9, VER-62 |
| Lovable “commit with batch ID in message” | Yes | Lovable Git sync documentation, 23 Oct 2026 | No | LOV1 |

## 7.2 Contradictions (Loop 3)

| Statement A | Statement B | Resolution | Fix |
| --- | --- | --- | --- |
| Phase 2: DEC-01 “Confirm … unless the team chooses React” (open) | Phase 5: “recommended in the current decision” (decided) | One status, from the tracker | CON1; VER-52 |
| Phase 2 table: G4, DEC-31, DEC-30, DEC-28, DEC-01 each block named work | Phase 2 gate and §10: only DEC-27 and DEC-16 before Part 0 | The table is right; the gate is incomplete | CON2; Gate Matrix |
| §5.1: paste Part 0; nothing else until it produces a working shell | §5.2: order is Batch 0, then S1… | VERIFY which builds the shell; state one order | CON3; VER-51 |
| §5.2: paste as written; don’t edit labels | DEC-16: choose display vocabulary once | Decisions are applied to the prompt document as a new version first | CON4 |
| Phase 1 gate: “Confirmed” results that change a screen go to Phase 2 | VER-48 “Disproved” would also change screens | “Any result that differs from the documents” | CON5 |
| Phase 5: “any unexpected field is a defect” | Phase 5: “a difference in … data is a defect” | Defects are missing, renamed or re-typed fields, and label, structure or state differences | CON6 |
| §0 and §5.3: never use any /static/... path | The app’s own CSS, JS and fonts likely live under /static | Ban tenant-upload paths only | INT6; VER-55 |
| §4 heading “JSON endpoints” | The list includes two .csv exports | Split JSON and file exports | INT9 |
| Phase 1 “Dossier claim” as a check | §0: never use the dossier | Checking a dossier claim is allowed; using it as a source is not. Say so. | CON11 |
| DEC-16 row: School admin/Teacher/Student or “the senior’s” Institute/Training Officer/Learner | Earlier DEC-08 (terminology) and DEC-16 (vocabulary) are separate decisions | Two rows, neutral options | CON10 |

# 8. Dependency graph and critical path

Effort ranges are assumptions for the senior developer to correct. They assume one senior developer, one front-end developer, one designer, two to three junior developers, part-time instructional design and DPO time, and a staging environment with its own Moodle.

LANE A  Safety and baseline   [Phase 0: rotate password (VER-59) →
  baseline VER-01 → walkthrough on demo tenant]
  2–4 days │
LANE B  Live checks           [Phase 1: VER-44..50 + carried items,
  on staging first; incident path if exposure]
  3–5 days  ─┐ │ (parallel)
LANE C  Contract              [Phase 3: contract rows per batch,
  routes without screens,        │ mock alignment]
  1–2 days per batch group  ─┘ │
LANE D  Decisions             [Phase 2: G-PRE decisions (DEC-01, 27,
  08/16, 32, 35, 39) → per-batch decisions as each batch approaches]
  rolling; G-PRE 1 week │
LANE E  Prototype             [Phase 4: Batch 0 → S1–S3 → L1–L8 →
  T1–T7 → A1–A2 → O1; each batch starts when its Gate Matrix row is
  closed] ~1–3 days per batch; 22 batches ≈ 5–8 weeks │      (Phase
  5 for batch n can start when batch n is accepted)
LANE F  Connection            [Phase 5: per screen, Definition of
  Done]   ~0.5–2 days per screen; 51 screens ≈ 6–10 weeks,
  overlapping Lane E │
LANE G  Verification          [Phase 6: CI tests continuously; LTI
  matrix, AGS, security, accessibility, performance on staging]
  2–3 weeks after last screen │
LANE H  Release               [Phase 7: R1–R5 gates → pilot
  institute → baseline → go-live] 1–2 weeks

Critical path:

- Phase 0 (password rotation, baseline).

- G-PRE decisions — DEC-01 above all.

- Batch 0 (shell, tokens; needs DEC-27, DEC-31, DEC-38).

- The longest chain of batches with their contract rows (learner batches L2–L4 carry the most decisions: DEC-09, DEC-10, DEC-18, DEC-30).

- Connection of the last screen.

- Phase 6 LTI and AGS checks (VER-20 is the known failure, and the riskiest single item).

- Release gates R2 and R3.

What shortens it most:

- signing DEC-01 and the G-PRE decisions in the first week;

- running Phase 1 and Phase 3 in parallel;

- starting connection of each batch as soon as it is accepted, instead of after all 22;

- putting the AGS fault-finding (VER-20) on its own track from week one, because it may take longest and blocks R3.

# 9. Improvement plan

Ranked by safety gained per unit of effort. Effort: S = under a day, M = a few days, L = a week or more.

## 9.1 Now — before any batch is pasted

| # | Improvement | Value | Effort | Owner | Findings |
| --- | --- | --- | --- | --- | --- |
| N1 | Rotate the demo password; search git history, drives and chat for copies; confirm environments don’t share credentials | Closes a live credential leak | S | Senior developer | SEC1, VER-59 |
| N2 | Write the incident path for confirmed live exposures and name the incident lead | Learner data protected the moment an exposure is found | S | Product owner + DPO | SEC2, DEC-33 |
| N3 | Settle DEC-01 and replace phase-wide gates with the per-batch Gate Matrix (G-PRE row first) | Stops work starting under contradictory gates | S–M | Senior developer + product owner | CON1, CON2, SEQ1, VER-52 |
| N4 | Apply signed decisions to the prompt document as a new version before pasting | No ad hoc label edits | S | Front-end developer | CON4, CON10, LRN3 |
| N5 | Set up Lovable properly: access level, public remix off, protected synced branch, project Knowledge, tag-per-batch, credit stop rule | Accepted batches can’t change silently; credits controlled | S | Senior developer | LOV1–LOV7, DEC-32, VER-58 |
| N6 | Define environments; staging with its own Moodle and two demo institutes; rules for live probes | Every later test has somewhere safe to run | M | Senior developer | OPS4, SEC3, DEC-34, DEC-35 |
| N7 | Expand the contract template; add routes without screens; align mocks per batch | Removes the main integration-defect source | M | Senior developer | INT2–INT4, INT9, INT10, SEQ2 |
| N8 | Split build assets from tenant uploads before acting on DEC-28 | Avoids breaking every page | S | Senior developer | INT6, VER-55 |
| N9 | Add the instructional designer to the RACI and learning checks to Phase 2 and Phase 4 | Learning design checked from the start | S | Product owner | LRN1, OPS1 |
| N10 | Review the walkthrough script; credentials from a secrets manager; demo tenant only; outputs stored securely | Safe baseline evidence | S | Senior developer | TST9, SEC8, VER-62 |

## 9.2 Next — before connection

| # | Improvement | Value | Effort | Owner | Findings |
| --- | --- | --- | --- | --- | --- |
| X1 | Adopt the 10-point Definition of Done per screen | One meaning of “done” | S | Senior developer + QA | OPS2, DEC-36 |
| X2 | Rewrite Phase 5 as “modify existing templates; keep handlers and guards” | Protects working code | S | Senior developer | INT1, CON6, CON12 |
| X3 | Cross-tenant and ID-guessing tests in CI from the first connected screen | The biggest risk tested continuously | M | QA + junior developers | TST1, TST8 |
| X4 | Usability round on the accepted prototype with trainees and instructors | Cheap fixes before code | M | Instructional designer + designer | LRN4 |
| X5 | Compute Citrus Mint and tenant-accent contrast | Accessible themes | S | Designer | LRN6, VER-57 |
| X6 | Trade-content review of mock and AI content | No unsafe procedures in demos | S | Product owner + trade instructor | LRN5, DEC-26 |
| X7 | Close or place carried items (VER-02/03, 07–10, 13, 20, 36–38) and decisions (DEC-02, 03, 09, 10, 19, 21, 22) | Integration blockers have owners | M | Senior developer | REF3, REF4, VER-53, VER-54 |
| X8 | Re-entry and change-control rules | Late discoveries handled in order | S | Senior developer | SEQ3, SEQ5, DEC-39 |

## 9.3 Later — before release or after the pilot

| # | Improvement | Value | Effort | Owner | Findings |
| --- | --- | --- | --- | --- | --- |
| L1 | LTI environment matrix and the AGS end-to-end check | Proves launch and grades where learners are | L | Senior developer + QA | TST2, TST3, TST10 |
| L2 | Security test list and pipeline hygiene | Known attacks tested | M | Senior developer | TST6, SEC6 |
| L3 | Accessibility and performance on the connected build | Works for every learner, on a phone | M | QA + front-end developer | TST4, TST5, LRN7 |
| L4 | Release gates R1–R5 with named signers; DPDP items | A complete, accountable release | M | Product owner | SEC7, OPS8 |
| L5 | Staged pilot, rollback, monitoring, support, training | A safe way in and out | M | Product owner + senior developer | OPS3, DEC-37 |
| L6 | Learning-gain baseline before learners start | The transformation can be shown to work | M | Instructional designer | LRN9, DEC-17 |
| L7 | Weekly tracker review; owners per document | Documents stay true | S | Senior developer | OPS5, OPS6 |
| L8 | Screenshot automation; mock types generated from the contract | Less manual effort, less drift | M | Front-end developer | LOV9, INT7 |

Answer to final challenge question 15 (the three improvements with the most safety for the least effort): N1 (rotate the password), N2 (incident path) and N3 (DEC-01 plus per-batch gates). All three are small, and all three are at the top of “Now”.

# 10. Open risks

What Version 3 cannot close on paper:

- Grade passback may still not work. VER-20 is a known failure. Version 3 makes the release depend on proof or on honest learner messaging, but the fault itself needs engineering time.

- Tenant isolation is unproven until VER-07 to VER-09, VER-05/06 and VER-44 are recorded with evidence, and the cross-tenant tests pass.

- The FINAL documents may already contain answers, or contradictions, this review could not see (VER-51 to VER-54, VER-66). Version 3’s references to FINAL sections must be re-checked when the files are available.

- Live exposure status is unknown. If VER-45 or VER-46 is confirmed, the incident path starts immediately and may delay everything else.

- Lovable’s behaviour can change between this review and the build. VER-58 must be re-checked on the build date.

- Learning outcomes are unproven. Version 3 adds checks and a baseline, but whether EdVidura improves learning is a pilot result (DEC-17), not a document property.

- Capacity. The effort ranges in Section 8 assume a staffing level not stated anywhere. If the team is smaller, the critical path lengthens, and the temptation to skip Phase 6 grows.

- Under-18 trainees. Until DEC-19 is signed, any pilot with ITI cohorts carries a children’s-data risk.

# 11. Release-gate record

## 11.1 Hard-stop conditions (review prompt §9)

| Condition | Result | Note |
| --- | --- | --- |
| A companion file is described without being opened, and has no VERIFY tag | Pass | Every FINAL-dependent claim carries VER-51 to VER-57 or VER-66 |
| A deliverable contains a password, key, token or real credential | Pass | The demo password is referred to by role only |
| A High finding has no fix, decision or VERIFY | Pass | All 21 High findings have a Version 3 fix; nine also carry a DEC or VER |
| Version 3 removes a check without a replacement, or weakens a gate or guard | Pass (on the specification) | Confirm against the Version 3 Change Table |
| A Strength is no longer true of Version 3 | Pass (on the specification) | STR1–STR9 kept; STR1’s “Never use” list narrowed to upload paths (INT6) — the intent is kept |
| Version 3 gates and summary disagree | Pass (on the specification) | The summary is copied from the Gate Matrix |
| DEC-01 described as both decided and open | Pass in Version 3 | Status comes from the tracker (VER-52) |
| No cross-tenant test, no grade-passback check, or no LTI matrix | Pass in Version 3 | TST1, TST2, TST3 fixed |
| The demo password is not rotated in Phase 0 | Pass in Version 3 | SEC1 |
| A confirmed exposure waits for release | Pass in Version 3 | SEC2, DEC-33 |
| No phase after Phase 4 checks learning purpose or vocabulary | Pass in Version 3 | Definition of Done item 8; Phase 6 walk-through; release gate R4 |
| A Lovable instruction contradicts current documentation | Pass | Checked 23 Oct 2026; re-check at build (VER-58) |
| Existing IDs renumbered, or new IDs collide | Pass, provisionally | New IDs start at DEC-32 and VER-51; re-check against the reviewed tracker |
| A score has no evidence | Pass | Every row in Section 3 cites IDs |

## 11.2 Final challenge questions (review prompt §11)

- Could institute A see institute B’s data without a test failing first? Under Version 2, yes: no test checks it. Under Version 3, Definition of Done item 6 and the CI cross-tenant tests should fail first. That holds only once those tests exist and RLS is proven (VER-07 to 09), so today it is unproven.

- Is there any point where a learner file is publicly reachable and the process waits? Version 2 waits. Version 3 starts the incident path the moment VER-45 is confirmed. Whether files are reachable now is unknown — no probe was run.

- Is the disclosed demo password still valid anywhere after Phase 0? Not if Version 3 Phase 0 is followed and VER-59 is recorded. Until then, assume it is valid.

- Can a new graduate tell, on any given day, whether they may paste the next batch, and from one place? In Version 3, yes: the Gate Matrix row for that batch. In Version 2, no.

- Will the mocks match the backend before the first batch? In Version 3, yes, for each batch whose contract rows and mock alignment are done (SEQ2). Not in Version 2.

- If Lovable’s Git sync changes an accepted batch, how would anyone notice? Version 3: the protected branch blocks most pushes, and each batch starts with a diff against the last accepted tag. Version 2 has no way to notice.

- Which routes with no screen could break the integration, and where are they? LTI login, launch, JWKS, deep-link return, AGS, NRPS, return-to-Moodle, exports, receipt and time-capsule JSON, ops retry, platform activation. Version 3 lists them in the Phase 3 routes-without-screens section.

- Does the Jinja path change any working handler, guard or test? Not in Version 3, unless a contract defect is logged and reviewed by the senior developer. Version 2’s wording invites it.

- When is grade passback proven, and what do learners see if it isn’t? Version 3: Phase 6 on staging Moodle, required by release gate R3. If it is not proven, learners see the honest “not sent” messages already defined in the Features Document. Today it is unproven (VER-20).

- Which browsers, devices and launch types are tested inside Moodle? Version 3: Chrome, Edge, Firefox and Safari (macOS and iOS), plus the Moodle mobile app on Android; iframe, new window and mobile app launches; learner, instructor and Training Officer roles. Untested in Version 2.

- At which phases is learning checked, and by whom? Version 3: Phase 2 (decisions), Phase 4 (learning intent, usability round), Phase 5 (Definition of Done item 8), Phase 6 (learner-loop walk-through) and Phase 7 (baseline, R4) — all by the instructional designer. Version 2: only indirectly, in Phase 4.

- Will the learning-gain baseline exist before the first learner uses the platform? Version 3 makes it part of the pilot rollout (DEC-37) and release gate R4. Version 2 doesn’t mention it.

- What exactly is “done” for one screen, and could two people disagree? Version 3: the 10 points in Definition of Done, each with evidence. Disagreement is possible only on judgement items (item 8), and the instructional designer signs those.

- If release goes wrong at the pilot, how do you roll back, and who decides? Version 3: a named rollback trigger and owner (DEC-37), with a backup taken before migration. Version 2 has no answer.

- Which three improvements give the most safety for the least effort? Rotate the password, write the incident path, and settle DEC-01 with per-batch gates — N1 to N3 in Section 9.1.

# Appendix A — New tracker rows (provisional numbers; check the reviewed tracker first)

## A.1 New decisions (Open)

| ID | Decision | Recommendation | Decider | Findings |
| --- | --- | --- | --- | --- |
| DEC-32 | Lovable workspace: plan, access, public remixing, who may push, branch protection, credit budget | Restricted access if the plan allows, otherwise a dedicated workspace with only the build team; public remixing off; only the Lovable app and the senior developer push to the synced branch; credit budget per batch | Senior developer + product owner | LOV2, LOV3, LOV7 |
| DEC-33 | Incident lead and response for live exposures | Senior developer as incident lead, with the DPO: contain → assess under DPDP → notify as the DPO decides → fix → re-test → record | Product owner + DPO | SEC2 |
| DEC-34 | Authorisation and logging of live checks; least privilege | Production read-only checks only with written approval and a log; designers use staging; unauthenticated probes listed in advance | Product owner + senior developer | SEC3, CON9 |
| DEC-35 | Environment model | Local, staging (own Moodle, demo tenants, synthetic learners), production; no real learner data outside production | Senior developer | OPS4, TST9 |
| DEC-36 | Definition of Done per screen | Adopt the 10-point Definition of Done in Version 3 (Phase 5) | Senior developer + QA | OPS2 |
| DEC-37 | Release rollout and rollback | One institute, one trade, one cohort first; rollback trigger and owner named; learning baseline before learners start | Product owner + senior developer | OPS3, LRN9 |
| DEC-38 | (formerly “G4”) Stickers, teleport link, report-a-problem | Omit stickers; add teleport and report-a-problem only after VER-60 and a privacy note | Product owner + DPO | REF1, SEC5, LRN8 |
| DEC-39 | Change control for companion documents during the build | Each batch built against named document versions; changes through the tracker; re-check affected batches only | Senior developer | SEQ5 |

## A.2 New VERIFY items (Open)

| ID | Claim to verify | Where to check | Who | Findings |
| --- | --- | --- | --- | --- |
| VER-51 | Whether Part 0 or Batch 0 builds the shell | Lovable Prompt Document FINAL | Front-end developer | CON3 |
| VER-52 | Whether DEC-01 is signed, and which option | Reviewed tracker | Senior developer | CON1 |
| VER-53 | Whether DEC-02, 03, 09, 10, 19, 21, 22 are closed | Reviewed tracker; Combined Summary v2 | Senior developer | REF4, SEC7 |
| VER-54 | Whether VER-02, 03, 07–10, 13, 20, 36, 37, 38 are closed | Reviewed tracker; Audit Report Verification | Senior developer | REF3 |
| VER-55 | What /static serves; where EPUBs are extracted | Repository | Senior developer | INT6 |
| VER-56 | Status code and template for denied, missing and cross-tenant records | Repository; staging | Junior developer with senior | CON8 |
| VER-57 | Citrus Mint and six tenant hues; contrast of every pair | Theme files; tenant settings | Designer + front-end developer | LRN6 |
| VER-58 | Lovable features on the team’s plan at build time | Lovable documentation and workspace settings | Front-end developer | LOV1–LOV4 |
| VER-59 | Demo password rotated; all copies found and removed | Identity store; repository history; drives | Senior developer | SEC1 |
| VER-60 | What the teleport link carries; what report-a-problem collects | Repository; design spec | Senior developer + DPO | SEC5 |
| VER-61 | Time-capsule export: content, format, tenant scope, personal data (audit claim 7) | Handler; staging | Senior developer | SEC5, INT10 |
| VER-62 | What edvidura_walkthrough.py does with credentials and output | The script | Senior developer | TST9 |
| VER-63 | Does any grade reach Moodle after Feedback Assist (audit claim 6) | Staging; grade-assist handler | Senior developer | REF1 |
| VER-64 | Is there a “Top Learners” table on school analytics (audit claim 8) | Staging; school_admin_analytics.html | Senior developer | LRN10 |
| VER-65 | The production EdVidura host (audit claim 23) | Deployment configuration | Senior developer | OPS4 |
| VER-66 | Status of the Learning Design Standard and Field Guide relative to the FINAL documents | Combined Summary v2; product owner | Product owner | REF2 |
| VER-67 | The real name of the app’s base Jinja template (Version 2 says base_shell.html) | Repository templates/ | Junior developer | CON12 |

# Appendix B — Gate and Dependency Matrix (condensed)

The full matrix, with columns for companion-document sections and status, is in the tracker additions (“Gate Matrix” tab).

| Gate | Screens | Decisions signed | VERIFY recorded | Signs |
| --- | --- | --- | --- | --- |
| G-PRE | All | DEC-01, 27, 08 + 16, 32, 35, 39 | VER-01, 51, 52, 58, 59 | Senior developer + product owner |
| Batch 0 | Shell, tokens, components | DEC-27, 31, 38, 04, 16 | VER-57, 60 | Senior developer + designer + instructional designer |
| S1 | SH-01, SH-02 | DEC-16, 23 | VER-21 | Front-end developer + senior developer |
| S2 | SH-03, SH-04, SH-07 | DEC-07 | VER-56, 40 | Front-end developer + senior developer |
| S3 | SH-05, SH-06 | DEC-02 | VER-24 | Senior developer |
| L1 | LR-01, LR-02 | DEC-28 | VER-33, 41, 55 | Front-end developer + instructional designer |
| L2 | LR-03, LR-04, LR-06 | DEC-30, 38 (DEC-20 noted, roadmap) | VER-20, 21, 42, 50 | Senior developer + instructional designer |
| L3 | LR-05 | — | VER-38, 31 | Front-end developer + senior developer |
| L4 | LR-07, LR-08, LR-10 | DEC-09, 10, 18 | VER-14, 15, 29, 43, 48 | Senior developer + instructional designer + DPO |
| L5 | LR-09, LR-11 | DEC-05 | VER-22, 43 | Front-end developer + instructional designer |
| L6 | LR-12, LR-13 | DEC-24, 30 | VER-21, 42, 49 | Front-end developer + DPO |
| L7 | LR-14, LR-15 | DEC-28, 06 | VER-10, 12, 15, 45, 55 | Senior developer |
| L8 | LR-16 | DEC-28 | VER-12, 45 | Senior developer |
| T1 | TC-01, TC-02, TC-05 | DEC-03, 26, 28 | VER-10, 13, 26, 33, 56 | Senior developer |
| T2 | TC-03, TC-04, TC-19 | DEC-03, 24 | VER-13, 16, 30 | Front-end developer + senior developer |
| T3 | TC-06, TC-07, TC-08 | DEC-09, 26 | VER-11, 19, 32 | Senior developer + instructional designer |
| T4 | TC-09, TC-10, TC-11 | DEC-09, 26 | VER-63 | Senior developer + instructional designer |
| T5 | TC-12, TC-13, TC-14 | DEC-18 | VER-43 | Front-end developer + DPO |
| T6 | TC-15, TC-16 | DEC-05, 26 | VER-11, 33 | Senior developer + instructional designer |
| T7 | TC-17, TC-18 | DEC-03 | VER-05, 06, 44 | Senior developer |
| A1 | SA-01, SA-02, SA-03 | DEC-04, 08 | VER-17 | Front-end developer + senior developer |
| A2 | SA-04 to SA-07 | DEC-24 | VER-18, 44, 49, 64 | Senior developer + DPO |
| O1 | OP-01, OP-02 | DEC-21, 34 | VER-61 | Senior developer |
| R1 Connection | All screens | DEC-36 | All batch items | Senior developer + QA |
| R2 Security and privacy | — | DEC-02, 03, 09, 19, 21, 22, 24, 28, 29, 33 | VER-07, 08, 09, 36, 37, 45, 46, 59, 60, 61 | Senior developer + DPO |
| R3 LTI and grades | — | DEC-22 | VER-02, 03, 20, 24, 25 | Senior developer + QA |
| R4 Learning | — | DEC-10, 16, 17, 26 | VER-35, 48 | Instructional designer + product owner |
| R5 Operations and rollout | — | DEC-35, 37 | VER-65 | Product owner + senior developer |