## README
EdVidura Process Review — tracker additions (run of the Process Review Prompt v1, 23 Oct 2026)
Mode B for the FINAL documents: they were not attached. New IDs (DEC-32–39, VER-51–67) are provisional — check against the reviewed tracker before pasting and renumber if taken (VER-52/VER-53 cover this).
Sheets: Gate Matrix (paste as tab "Gate Matrix"); New Decisions; New VERIFY; Review Findings (78, with where Version 3 fixes each); Strengths (keep); Change Table (Version 2 → Version 3).
No credentials appear anywhere in this workbook.

## Gate Matrix
Gate | Screens | Decisions signed | VERIFY recorded | Contract rows | Companion sections at agreed version | Signs the gate | Status
G-PRE (before any batch) | All | DEC-01, DEC-27, DEC-08 + DEC-16 (vocabulary), DEC-32 (Lovable workspace), DEC-35 (environments), DEC-39 (change control) | VER-01 baseline, VER-51, VER-52, VER-58, VER-59 (password rotated) | Shell context (user name, role label, institute, course); session-expiry behaviour (VER-38) | Lovable FINAL Part 0, authority section; tracker version recorded | Senior developer + product owner | Open
Batch 0 (shared foundations) | Shell, tokens, shared components | DEC-27, DEC-31, DEC-38 (teleport, report-a-problem), DEC-04 (menus for instructor-admins), DEC-16 | VER-57 (contrast), VER-60 | Shell context; access page behaviour (VER-56) | Lovable FINAL Batch 0; Addendum V shell labels | Senior developer + designer + instructional designer | Open
S1 | SH-01, SH-02 | DEC-16, DEC-23 | VER-21 | GET / ; GET /launch-hub (context) | Features FINAL App. C rows; Addendum V | Front-end developer + senior developer | Open
S2 | SH-03, SH-04, SH-07 | DEC-07 | VER-56, VER-40 | access.html context; GET/POST /receipts/verify; GET/POST /lti/register | Features FINAL App. C; Addendum V | Front-end developer + senior developer | Open
S3 | SH-05, SH-06 | DEC-02 | VER-24 | /lti/deep-link; /onboard (GET/POST); /onboard/platform/{id}/active | Features FINAL App. A, C | Senior developer | Open
L1 | LR-01, LR-02 | DEC-28 | VER-33, VER-41, VER-55 | GET /lessons; GET /lessons/{id}; complete/uncomplete POST | Features FINAL App. C; Addendum V (lesson) | Front-end developer + instructional designer | Open
L2 | LR-03, LR-04, LR-06 | DEC-30, DEC-38, DEC-20 (noted only — roadmap) | VER-20 (grade-state values), VER-21, VER-42, VER-50 | GET /active-quizzes; GET /quiz (gate state); GET /quiz/result/{attempt_id}; receipt.json | Addendum V (quiz result banners) | Senior developer + instructional designer | Open
L3 | LR-05 | — | VER-38, VER-31 | GET /quiz (session state); POST /quiz/submit | Addendum V (quiz) | Front-end developer + senior developer | Open
L4 | LR-07, LR-08, LR-10 | DEC-09, DEC-10, DEC-18 | VER-14, VER-15, VER-29, VER-43, VER-48 | /learn/coach; /learn/coach/ask; /learn/coach/feedback; /learn/coach/shortcuts; /learn/ai/hint; /learn/flashcards | Addendum V (Ask Vidura) | Senior developer + instructional designer + DPO | Open
L5 | LR-09, LR-11 | DEC-05 | VER-22, VER-43 | /learn/gap; /learn/micro | Features FINAL App. C | Front-end developer + instructional designer | Open
L6 | LR-12, LR-13 | DEC-24, DEC-30 | VER-21, VER-42, VER-49 | /learn/analytics; /learn/activity | Features FINAL App. C | Front-end developer + DPO | Open
L7 | LR-14, LR-15 | DEC-28, DEC-06 | VER-10, VER-12, VER-15, VER-45, VER-55 | /manuals; /manuals/{id}; /api/v1/manuals/{id}/progress, bookmarks, annotations; epub-files route | Features FINAL App. A, C | Senior developer | Open
L8 | LR-16 | DEC-28 | VER-12, VER-45 | /read/manuals/{id} | Features FINAL App. C | Senior developer | Open
T1 | TC-01, TC-02, TC-05 | DEC-03, DEC-26, DEC-28 | VER-10, VER-13, VER-26, VER-33, VER-56 | /teacher/attempts (+ .csv); /teacher/content; lesson and question POSTs; /teacher/manuals (uploads, versions, publish) | Features FINAL App. A, C | Senior developer | Open
T2 | TC-03, TC-04, TC-19 | DEC-03, DEC-24 | VER-13, VER-16, VER-30 | /teacher/analytics (+ .json, .csv, live.json); /teacher/activity; /lti-integration | Features FINAL App. C | Front-end developer + senior developer | Open
T3 | TC-06, TC-07, TC-08 | DEC-09, DEC-26 | VER-11, VER-19, VER-32 | /teacher/ai; generate; generate-from-pdf; save; author; author/apply | Features FINAL App. A, C | Senior developer + instructional designer | Open
T4 | TC-09, TC-10, TC-11 | DEC-09, DEC-26 | VER-63 | remediation (+ save); simplify (+ apply); grade-assist | Features FINAL App. C | Senior developer + instructional designer | Open
T5 | TC-12, TC-13, TC-14 | DEC-18 | VER-43 | /teacher/coach/insights; /teacher/coach/shortcuts; /teacher/skills | Features FINAL App. C | Front-end developer + DPO | Open
T6 | TC-15, TC-16 | DEC-05, DEC-26 | VER-11, VER-33 | /teacher/sme; /teacher/dct (+ generate, reel) | Features FINAL App. C | Senior developer + instructional designer | Open
T7 | TC-17, TC-18 | DEC-03 | VER-05, VER-06, VER-44 | /institutions; /student-directory | Features FINAL App. C | Senior developer | Open
A1 | SA-01, SA-02, SA-03 | DEC-04, DEC-08 | VER-17 | /school-admin; /school-admin/teachers; /school-admin/classes (+ add, link-course, bind-moodle) | Features FINAL App. C | Front-end developer + senior developer | Open
A2 | SA-04, SA-05, SA-06, SA-07 | DEC-24 | VER-18, VER-44, VER-49, VER-64 | /school-admin/students; /school-admin/analytics (+ live.json); /school-admin/activity; /institution-detail | Features FINAL App. C | Senior developer + DPO | Open
O1 | OP-01, OP-02 | DEC-21, DEC-34 | VER-61 (exports reviewed) | /ops/login; /ops/dashboard; /ops/retry-lrs | Features FINAL App. A | Senior developer | Open
R1 Connection complete | All screens | DEC-36 | All batch VERIFY items | Every App. C screen + routes without screens | All | Senior developer + QA | Open
R2 Security and privacy | — | DEC-02, DEC-03, DEC-09, DEC-19, DEC-21, DEC-22, DEC-24, DEC-28, DEC-29, DEC-33 | VER-07, VER-08, VER-09, VER-36, VER-37, VER-45, VER-46, VER-59, VER-60, VER-61 | — | Privacy notice; DPDP items | Senior developer + DPO | Open
R3 LTI and grades | — | DEC-22 | VER-02, VER-03, VER-20, VER-24, VER-25 | LTI login, launch, JWKS, deep-link return, AGS, NRPS, return-to-Moodle | LTI environment matrix results | Senior developer + QA | Open
R4 Learning | — | DEC-10, DEC-16, DEC-17, DEC-26 | VER-35 (trade content), VER-48 | — | Learning Design Standard version agreed (VER-66) | Instructional designer + product owner | Open
R5 Operations and rollout | — | DEC-35, DEC-37 | VER-65 | — | Runbook, monitoring, rollback plan, training plan | Product owner + senior developer | Open

## New Decisions
ID | Decision | Options | Recommendation | Decider | Linked findings | Decision taken | Decided by | Date | Status
DEC-32 | Lovable workspace set-up: plan, project access, public remixing, who may push to the synced branch, branch protection, credit budget | Current plan with Workspace access · Business/Enterprise with Restricted access | Restricted access if the plan allows, otherwise a dedicated workspace with only the build team; public remixing off; protect the synced branch (only the Lovable app and the senior developer push); credit budget per batch recorded | Senior developer + product owner | LOV2, LOV3, LOV7 |  |  |  | Open
DEC-33 | Incident lead and response for live exposures (e.g. VER-45, VER-46) | Ad hoc · Named incident lead with a written path | Named incident lead (senior developer) and DPO; path: contain → assess personal-data impact under DPDP → notify as the DPO decides → fix → re-test → record | Product owner + DPO | SEC2 |  |  |  | Open
DEC-34 | Authorisation and logging for live checks on production; least-privilege access | Anyone with access · Approved, logged checks; staging first | Read-only checks on production only with written approval and a log; designers use staging; unauthenticated probes listed in advance | Product owner + senior developer | SEC3, CON9 |  |  |  | Open
DEC-35 | Environment model | Local + production only · Local, staging (with its own Moodle and demo tenants), production | Local, staging and production; demo tenants and synthetic learners on staging; no real learner data outside production | Senior developer | OPS4, TST9 |  |  |  | Open
DEC-36 | Definition of Done per screen | Phase-by-phase checks · One per-screen Definition of Done | Adopt the 10-point Definition of Done in Version 3 §6.3 | Senior developer + QA | OPS2 |  |  |  | Open
DEC-37 | Release rollout and rollback | Big-bang · Staged pilot | One institute, one trade, one cohort first; rollback trigger and owner named; learning-gain baseline captured before learners start | Product owner + senior developer | OPS3, LRN9 |  |  |  | Open
DEC-38 | (formerly "G4") Stickers, teleport link, report-a-problem | As G4 recommendation · With security and privacy design | Omit stickers (no gamification); add teleport link and report-a-problem only after VER-60 and a privacy note (what is collected, who sees it, retention) | Product owner + DPO | REF1, SEC5, LRN8 |  |  |  | Open
DEC-39 | Change control for companion documents during the build | No freeze · Freeze per batch with re-baseline rule | A batch is built against a named version of the FINAL documents; changes go through the tracker and trigger re-check of affected batches only | Senior developer | SEQ5 |  |  |  | Open

## New VERIFY
ID | Claim to verify | Why it matters | Where to check | Who | Evidence recorded | Date | Status
VER-51 | Whether Part 0 or Batch 0 builds the shell in the FINAL Lovable document | §5.1 and §5.2 disagree | Lovable Prompt Document FINAL, Part 0 and Batch 0 | Front-end developer |  |  | Open
VER-52 | Whether DEC-01 is signed, and which option | Decides whether Lovable work and Phase 5 may start, and which branch applies | Reviewed tracker, Decision Log | Senior developer |  |  | Open
VER-53 | Whether DEC-02, 03, 09, 10, 19, 21, 22 are closed | They block safe release but are missing from Phase 2 | Reviewed tracker; Combined Summary v2 | Senior developer |  |  | Open
VER-54 | Whether VER-02, 03, 07–10, 13, 20, 36, 37, 38 are closed | They block safe integration but have no phase | Reviewed tracker; Audit Report Verification | Senior developer |  |  | Open
VER-55 | What /static serves (build CSS/JS/fonts vs tenant uploads) and where EPUBs are extracted | DEC-28 may break the app's own assets | Repository: static mount and upload paths | Senior developer |  |  | Open
VER-56 | Status code and template returned for denied, missing and cross-tenant records | Contract "Errors" column | Repository handlers; live check on staging | Junior developer with senior |  |  | Open
VER-57 | Citrus Mint hex values and the six tenant hues; contrast of every pair | DEC-27, DEC-31 | Repository theme files; tenant settings | Designer + front-end developer |  |  | Open
VER-58 | Lovable features on the team's plan at build time: Git sync behaviour, project Knowledge, revert, access levels, public-remix setting | Version 3 Lovable routine relies on them | Lovable documentation and workspace settings on the build date | Front-end developer |  |  | Open
VER-59 | Demo password rotated; all copies found and removed (documents, git history, chat, drives) | A disclosed credential stays valid until rotated | Identity store; repository history; shared drives | Senior developer |  |  | Open
VER-60 | What the teleport link carries (IDs, tokens) and what report-a-problem collects | Security and privacy of DEC-38 items | Repository; design spec | Senior developer + DPO |  |  | Open
VER-61 | Time-capsule export (audit claim 7): content, format, tenant scope, personal data | Data export with no review | /teacher/time-capsule.json handler; live check | Senior developer |  |  | Open
VER-62 | What edvidura_walkthrough.py does with credentials and where it writes output | It runs with real accounts | The script itself | Senior developer |  |  | Open
VER-63 | After Feedback Assist, does any grade reach Moodle (audit claim 6) | Must be copy-only unless decided | Live check on staging; grade-assist handler | Senior developer |  |  | Open
VER-64 | Is there a "Top Learners" table on school analytics (audit claim 8) | Would be a leaderboard (LRN10) | Live check; school_admin_analytics.html | Senior developer |  |  | Open
VER-65 | The production EdVidura host (audit claim 23) | Environments and probes | Deployment configuration | Senior developer |  |  | Open
VER-66 | Status of the Learning Design Standard and Developer Field Guide relative to the FINAL documents | New graduates need to know which to read | Combined Summary v2; product owner | Product owner |  |  | Open
VER-67 | The real name of the app's base Jinja template | Version 2 assumes base_shell.html | Repository templates/ | Junior developer |  |  | Open

## Review Findings
ID | Severity | Finding | Source | Fixed in Version 3 (sections) | Decision / VERIFY | Status
CON1 | High | DEC-01 is presented as both open and decided. Phase 2 lists it with the recommendation "Confirm" ("…unless the team chooses React"). Phase 5 says "recommended in the current decision". Phase 4 is blocked by DEC-01, yet the Phase 2 gate and the §10 summary name only DEC-27 and DEC-16. A reader cannot tell whether Lovable work may start. | Seed (confirmed, Mode B) | Phase 2 DEC-01 | VER-52 | Open
CON2 | High | Gate lists disagree. The Phase 2 table says G4 blocks "L2 and Batch 0 shell", DEC-31 blocks "any themed screen", DEC-30 blocks L2/L6, DEC-28 blocks "any screen that shows a file", and DEC-01 blocks Phases 4 and 5. The Phase 2 gate and the summary require only DEC-27 and DEC-16 before Part 0. Batch 0 could be built before G4 is decided. | Seed (confirmed, Mode B) | Appendix A (new); Phase 2; Phase 2 gate; §10 Summary; §5.2 |  | Open
CON4 | High | "Paste the batch as written; do not edit label text" vs DEC-16 "choose once". If the chosen display vocabulary differs from the batch text, someone must update the prompt document before pasting. No step says who, when, or how it is recorded. | Seed (confirmed, Mode B) | §3.3 (new) |  | Open
INT1 | High | The Jinja path is written as greenfield. "Rebuild each accepted batch as a Jinja template… implement the route or the template with the guard." But the routes, guards and templates already exist. The wording invites rewriting working, tested code. Version 3 should say: change the existing template to match the accepted design; do not change the handler, guard or context unless a contract defect is logged and reviewed; keep existing tests passing. | Seed (confirmed, Mode B) | §6.1 Jinja branch; §6.2 step 1 |  | Open
INT2 | High | The contract has no columns for the things that break integrations. Missing: session and authentication (cookie, LTI context); CSRF token fields; enumerations and state values (for example grade_sent, grade_error, ags_available); nullability; limits and pagination; time format (stored in UTC, shown in IST); which IDs may never be displayed; upload size and type limits; empty and error states; tenant scope of the data. | Seed (confirmed, Mode B) | Phase 3 contract |  | Open
INT4 | High | Routes without screens are outside the contract. The gate covers "every Appendix C screen", but integration also depends on routes with no screen: LTI login, launch, JWKS, deep-link return, AGS, NRPS, return-to-Moodle, CSV/JSON exports, receipt JSON, time-capsule JSON, ops retry, platform activation. Add a contract section for them. | Seed (confirmed, Mode B) | Phase 3 gate; §4.4 (new) |  | Open
INT6 | High | DEC-28 "remove the /static mount" may break the app's own CSS, JS and fonts. Those are usually served from /static. The real problem is user uploads (extracted EPUBs under /static/uploads/epub/). Separate public build assets from tenant uploads; only uploads move behind authenticated, tenant-scoped routes. Also, "never use any /static/... path" in §0 and §5.3 must not ban the app's own stylesheet. VERIFY against the code. | Seed (confirmed, Mode B) | Phase 2 DEC-28; §0 Never use; §5.3 | VER-55 | Open
LOV2 | High | Git sync is two-way. Commits pushed to the synced branch appear in the Lovable project. If histories diverge, Lovable pushes to a separate lovable-sync branch instead. Force-pushing or rewriting history on the synced branch is discouraged. The process must say who may push to the prototype repository, and must protect the branch. Otherwise an accepted batch can change silently. [EXTERNAL] | Seed (confirmed, Mode B) | §5.1; §5.1 Lovable setup; §5.4 | DEC-32 | Open
LRN1 | High | The process never checks learning design. No instructional-design role, no learning-purpose check when screens are connected or released. The Learning Design & Transformation Standard isn't in the file list. The only trace is "Batch 0's common checklist items 1–19". For a platform whose claim is better learning, every phase that touches a screen must check its learning purpose, the learner vocabulary, and that roadmap items aren't built by accident. | Seed (confirmed, Mode B) | §0 Files; §5.3 (new items) | VER-66 | Open
LRN3 | High | DEC-16: "use code values for everything the backend sends". This risks backend enum values reaching learner text — the "AGS off" problem. Add a display-mapping layer (the i18n strings file): code values stay in data, and learners see plain words. | Seed (confirmed, Mode B) | Phase 2 DEC-16 |  | Open
LRN5 | High | No trade-content safety review. Mock and AI-generated electrical content must be reviewed by a qualified trade instructor before learners or demo audiences see it (DEC-26). An unsafe step is a hazard, not a typo. | Seed (confirmed, Mode B) | §5.5 (new) | DEC-26, VER-35 | Open
OPS2 | High | No Definition of Done per screen. A screen is done when it has: a contract row; an accepted batch (tagged); a connected template with guard tests; a cross-tenant test; accessibility and vocabulary checks; a live check with evidence; and a tracker row. Version 2 has pieces of this in four phases. | Seed (confirmed, Mode B) | Phase 5 gate; §0 Files; §6.3 (new) | DEC-36 | Open
OPS3 | High | Release has no rollout, rollback or operations plan. Missing: environments; database backup before migration; migration order; a staged rollout (one institute, one cohort); monitoring and alerts (launch failures, grade-passback failures, LRS outbox backlog); a support route for institutes; instructor training (Train the Trainer); communication. | Seed (confirmed, Mode B) | §8.1 Release; §8.2 (new) | DEC-37 | Open
SEC1 | High | The demo password was disclosed, and removing it from documents doesn't revoke it. Version 2 handles it in Phase 7 ("removed from the audit report"). It must be rotated now (Phase 0). Then: search git history, shared drives and chat for copies; confirm other environments use different credentials. | Seed (confirmed, Mode B) | Phase 0; Phase 0 gate; §0 Never use; §8.1 | VER-59 | Open
SEC2 | High | Live exposure checks have no incident path. If VER-45 (unauthenticated access to extracted eBook files) or VER-46 (internal pages reachable when logged out) is confirmed on production, learner content is exposed now. Version 2 records the result and waits for Phase 2 and release. Version 3 needs: immediate mitigation, who to notify, a DPDP breach assessment, and evidence of the fix. | Seed (confirmed, Mode B) | Phase 1 table; §2.3 (new) | DEC-33 | Open
SEC7 | High | DPDP items absent from the release gate. Missing: privacy notice; what instructors can see; under-18 handling (DEC-19); retention (DEC-24); where AI model calls send learner data (DEC-09). | Seed (confirmed, Mode B) | §8.1 Release |  | Open
SEQ2 | High | No step aligns the Lovable mock-data contract with the API contract. The Lovable document's Batch 0 already defines mock modules, written from documents. Phase 3 produces a code-derived contract, but nothing tells anyone to update Batch 0 and Part 0 to match before pasting. That is exactly the divergence Phase 3 warns about. | Seed (confirmed, Mode B) | §4.5 (new) |  | Open
TST1 | High | No cross-tenant test anywhere. Phase 6 tests roles (learner vs teacher vs admin) but never institute A vs institute B. That is the platform's biggest risk. Also missing: guessing another learner's IDs on /quiz/result/{attempt_id}, receipts, manuals and the annotations API; and course-scope tests (DEC-03). | Seed (confirmed, Mode B) | §7.1 (new) |  | Open
TST2 | High | Grade passback is never verified. No phase checks AGS end to end, despite the known token.php / null-JWKS failure. Release must either prove it, or confirm that every learner-facing message says honestly that grades were not sent. | Seed (confirmed, Mode B) | §7.1 (new); §8.1 R3 |  | Open
TST3 | High | No LTI environment matrix. Missing: Safari (macOS and iOS), third-party-cookie behaviour inside the Moodle iframe, the Moodle mobile app on Android, deep linking, session expiry mid-quiz (VER-38). | Seed (confirmed, Mode B) | §7.2 (new) |  | Open
TST6 | High | No security test list. Missing: CSRF; framing (frame-ancestors); malicious EPUB; CSV formula injection; upload limits; rate limiting on /onboard and /ops/login; secrets in templates and logs. | Seed (confirmed, Mode B) | §7.1 (new) |  | Open
CON10 | Medium | DEC-16 row conflates two earlier decisions: DEC-08 (UI terminology: School/Institute etc.) and DEC-16 (one learner vocabulary). It also names one option as "the senior's", which personalises a product decision. State options neutrally and keep the two decisions distinct. | New in this run | Phase 2 DEC-16 | DEC-08, DEC-16 | Open
CON3 | Medium | Part 0 vs Batch 0. §5.1 step 3 says paste Part 0 and "do not paste anything else until Part 0 has produced a working shell". In the Lovable document lineage, Part 0 is the master prompt and Batch 0 builds the shell, tokens and shared components. §5.2 then lists the order as "Batch 0, then S1…". VERIFY against the FINAL Lovable document which one produces the shell, and make §5.1 and §5.2 agree. | Seed (confirmed, Mode B) | §5.1 step 3 | VER-51 | Open
CON5 | Medium | Phase 1 gate logic is incomplete. Only "Confirmed" results that change a screen go to Phase 2. A "Disproved" result can also change a screen — for example, if VER-48 shows the live labels differ from Addendum V, the specification is wrong. The rule should be "any result that differs from the documents". | Seed (confirmed, Mode B) | Phase 1 gate |  | Open
CON6 | Medium | Phase 5 defect rules are too strict and too loose at once. "Any unexpected field is a defect" fails harmless additions. "A difference in label or data is a defect" fails every screen, because mock data never equals live data. The rule should be: missing, renamed or re-typed fields; label differences; structure or state differences. | Seed (confirmed, Mode B) | §6.2 step 3; §6.2 step 4 |  | Open
CON8 | Medium | Error contract assumes JSON-style status codes. The server-rendered app returns access.html from many routes. Record the real status code and template per error (VERIFY). | Seed (confirmed, Mode B) | Phase 3 contract | VER-56 | Open
INT10 | Medium | /quiz/result/{attempt_id}/receipt.json and /teacher/time-capsule.json are data exports with no screen, no privacy review and no learner-wording rule (raw JSON to learners was ruled out earlier; the learner button became "Download receipt file"). Add them to the routes-without-screens contract with a personal-data note. | New in this run | Phase 1 table; §4.4 | VER-40, VER-61 | Open
INT3 | Medium | Server-rendered screens have no "response JSON". Their contract is the template context (variable names and types) plus the form field names. Say so, or juniors will invent JSON shapes for pages that render HTML. | Seed (confirmed, Mode B) | §4.2 (new) |  | Open
INT5 | Medium | The React branch understates the work. Most pages have no JSON endpoint today. The React path also needs CSRF, the iframe cookie strategy (DEC-22), LTI bootstrap and a CSP. "Build the API layer first" should list these or point to the DEC-01 decision record. | Seed (confirmed, Mode B) | §6.1 React branch | DEC-01, DEC-22 | Open
INT7 | Medium | Manual contract checks will not survive change. Recommend: generate the Lovable mock types from the contract; add response or context schema tests in the backend; run them in CI. | Seed (confirmed, Mode B) | §4.5 (new); §4.6 (new) |  | Open
LOV1 | Medium | "Commit it to GitHub with the batch ID in the message" isn't how Lovable's Git sync works. Lovable commits and pushes edits itself through its GitHub app, attributing them to the member who made the change. Its documentation describes no per-change commit message. Use a git tag on the synced branch per accepted batch (for example batch-S1-accepted) and record the commit SHA in the tracker. [EXTERNAL] | Seed (confirmed, Mode B) | Phase 4 gate; §5.2 |  | Open
LOV3 | Medium | Project access is not stated. Lovable projects default to Workspace access. Restricted (invited users only) is a Business/Enterprise feature. A separate public-remix setting lets anyone with the link see a preview and copy the project. The process should name the plan, the access level and "public remixing off". [EXTERNAL] | Seed (confirmed, Mode B) | §5.1 Lovable setup | DEC-32 | Open
LOV4 | Medium | Hard rules are pasted once and then drift. Lovable supports persistent project-level instructions (project Knowledge). Putting Part 0's hard rules there reduces drift across long sessions. VERIFY the current feature and its limits. [EXTERNAL] | Seed (confirmed, Mode B) | §5.1 |  | Open
LOV5 | Medium | The network-panel check will produce false failures. The Lovable preview and the Vite dev server load their own scripts, hot-reload connections and assets. Re-word it: no request to any API, authentication, database or third-party data host. Self-hosted fonts and the app's own static files are allowed. | Seed (confirmed, Mode B) | §5.3 |  | Open
LOV6 | Medium | Dependency drift isn't checked. Lovable may add packages (Supabase, Firebase, HTTP clients, analytics) or environment files without being asked. Add a per-batch check of package.json, .env* and any supabase/ folder against the previous accepted tag. | Seed (confirmed, Mode B) | §5.2 |  | Open
LOV7 | Medium | No stop rule for credits. Add a rule such as: after two failed corrections on the same problem, revert to the last accepted tag and re-prompt a smaller scope. Also set a credit budget per batch, and record credits spent in the tracker. | Seed (confirmed, Mode B) | §5.1; §5.2 |  | Open
LRN10 | Medium | Phase 1 "Top Learners" table: if it exists it is a ranking of learners — a leaderboard. The earlier standard bans leaderboards and individual ranking (principle 12, ethical analytics). The recommendation should be "remove unless the product owner records a reason", not an open choice. | New in this run | Phase 1 table | VER-64 | Open
LRN2 | Medium | DEC-30: a constant 60% pass mark. Acceptable for now, and better than an unexplained threshold. But competence thresholds belong to the course or skill. Show learners where the 60% comes from, and record a configurable threshold as a roadmap item. [LEARNING-SCIENCE: valid assessment] | Seed (confirmed, Mode B) | Phase 2 DEC-30 |  | Open
LRN4 | Medium | No usability check with real users before connection. Five ITI trainees on their own phones and two instructors, walking through the accepted prototype, would catch vocabulary and flow problems cheaply. | Seed (confirmed, Mode B) | Phase 4 gate; §5.5 (new) |  | Open
LRN6 | Medium | DEC-27 "Citrus Mint" and DEC-31 tenant accents need computed contrast. Mint and citrus hues are often light, and white text on them often fails 4.5:1. Compute every pair: white on accent; accent as text on the page and on surfaces (4.5:1); the accent as a focus or control boundary (3:1). Define the "six hues". [CALC] | Seed (confirmed, Mode B) | Phase 2 DEC-27; Phase 2 DEC-31 | VER-57 | Open
LRN7 | Medium | IST display, Indic scripts and slow-network states are not in any acceptance or live check. | Seed (confirmed, Mode B) | §5.3 (new items) |  | Open
LRN9 | Medium | No baseline for measuring learning. The pilot plan (DEC-17) needs knowledge and practical baselines captured before learners use the platform. Release is the last chance; Version 2 doesn't mention it. | Seed (confirmed, Mode B) | §8.2 (new) | DEC-37 | Open
OPS1 | Medium | Owners are roles only; juniors are invisible. Add a RACI per phase, with a named approver per gate and the junior developers' tasks. | Seed (confirmed, Mode B) | Phase 0 gate; Phase 3; Phase 6 gate; §0B (new) |  | Open
OPS4 | Medium | Environments are never defined. "Local", "the Moodle deployment", "the live deployment" and "production" are used loosely. Define local, staging and production, which checks run where, and which data is real. | Seed (confirmed, Mode B) | Phase 1 table; §0A (new) | DEC-34, DEC-35 | Open
OPS8 | Medium | Phase 7 sign-off is product owner + senior developer only; no QA, security/DPO or instructional-design sign-off on the release. | New in this run | §0B (new); §8.1 Release; §8.3 (new) |  | Open
REF1 | Medium | Mixed identifier schemes. DEC-nn, VER-nn, "G4", "audit claim 6/7/8/23". Audit claims and G4 are not tracker rows. They are not in the Phase 1 gate (VER-44 to 50 only) or in the release list. Give each a tracker ID or state where it lives. | Seed (confirmed, Mode B) | Phase 0; Phase 1 gate; Phase 1 table; Phase 2 G4 | DEC-38, VER-53, VER-60, VER-61, VER-63, VER-64, VER-65 | Open
REF2 | Medium | Companion documents from the enhancement package are missing from §0. The Learning Design & Transformation Standard, the Developer Field Guide and the Decision/VERIFY/Change Logs have no status. Are they current, merged into FINAL, or superseded? New graduates won't know whether to read them. | Seed (confirmed, Mode B) | §0 Files | VER-66 | Open
REF3 | Medium | Only VER-01 and VER-44 to VER-50 appear in the process. Earlier VERIFY items that block safe integration have no phase. Examples: role mapping (VER-02/03), RLS forced and SET LOCAL (VER-07 to 09), EPUB serving (VER-10), CSV formula injection (VER-13), AGS (VER-20), CSRF (VER-36), framing (VER-37), quiz answers on session expiry (VER-38). Each needs a phase, or an explicit statement that FINAL closed it. | Seed (confirmed, Mode B) | Phase 1 gate; Phase 3; §2.2 (new) | VER-02, VER-53, VER-61 | Open
REF4 | Medium | Decisions missing from Phase 2. DEC-02 (/onboard), DEC-03 (instructor scope), DEC-09 (model provider and data residency), DEC-10 (the coach during an open graded quiz), DEC-19 (under-18 trainees), DEC-21 (ops authentication) and DEC-22 (iframe cookies) block safe release, but are not listed. VERIFY whether FINAL closed them. | Seed (confirmed, Mode B) | Phase 2; Phase 2 (new rows) | DEC-02 | Open
SEC3 | Medium | Probing production needs authorisation. Unauthenticated requests and signed-in checks on the live deployment should be approved, logged and, where possible, run on a staging copy. | Seed (confirmed, Mode B) | Phase 0; Phase 1; §0A (new) | DEC-34, DEC-35, VER-62 | Open
SEC4 | Medium | DEC-29 "decide per table" gives no criteria. lti_platforms holds registration data (issuer, client IDs, possibly key references) and institutions holds tenant records. State the criteria: what reads them, before tenant resolution or after; who must never see other rows; how tests prove it. | Seed (confirmed, Mode B) | Phase 2 DEC-29 |  | Open
SEC5 | Medium | New features need review. The teleport link (G4) may carry identifiers or tokens across contexts. Report-a-problem collects free text and possibly screenshots, which are personal data. The time-capsule export (audit claim 7) is a data export needing tenant-scope and personal-data review. None has a security or privacy step. | Seed (confirmed, Mode B) | Phase 1 table; Phase 2 G4 | DEC-38, VER-60 | Open
SEC6 | Medium | No secure-delivery hygiene. Missing: threat model; dependency and secret scanning; static analysis in the pipeline. | Seed (confirmed, Mode B) | §7.1 | DEC-21 | Open
SEC8 | Medium | Phase 0 keeps walkthrough REPORT.md and screenshots of live accounts. These may contain learner personal data; store them in an access-controlled location, not in the documents folder or chat. | New in this run | Phase 0 |  | Open
SEQ1 | Medium | Fully serial waterfall. Phase 4 can't start until every Appendix C screen has a contract row, and every phase waits for the previous one. Phase 1 live checks and the Phase 3 contract can run in parallel. Per-batch gating would let Batch 0 and S1 start once their own decisions and contract rows are closed. | Seed (confirmed, Mode B) | Appendix A (new); Phase 1; Phase 3 gate; §0 Files; §12 (new); §5.2 | DEC-34 | Open
SEQ3 | Medium | No re-entry rules. When Phase 5 or 6 finds that the contract, a label or a decision was wrong, which phase do you return to? What gets updated — the prototype, the prompt document, the template? Who decides? | Seed (confirmed, Mode B) | §11 (new) |  | Open
SEQ4 | Medium | No critical path, durations or milestones. The team can't plan capacity or see slippage. | Seed (confirmed, Mode B) | §12 (new) |  | Open
SEQ5 | Medium | Change control during the build. What happens if a FINAL document changes while batches are being built? Freeze rule, re-baseline rule. | Seed (confirmed, Mode B) | Phase 8 | DEC-39 | Open
TST10 | Medium | Phase 6 omits NRPS roster sync, deep linking and a re-run of the test suite on the connected build; /onboard is never tested. | New in this run | §7.1 (new) |  | Open
TST4 | Medium | Accessibility is tested on the prototype only. The connected Jinja build needs its own WCAG 2.2 AA pass: keyboard, screen reader, contrast, focus on themed tenant pages. | Seed (confirmed, Mode B) | §7.1 (new) |  | Open
TST5 | Medium | No performance or low-bandwidth test. Learners use mid-range Android phones on mobile data. Set page-weight and load-time budgets, and test the EPUB reader and uploads on a throttled connection. | Seed (confirmed, Mode B) | §7.1 (new) |  | Open
TST7 | Medium | No evidence format. Each check should record environment, commit, account role, timestamp, result, and a screenshot or HTTP log. Without this, "Verified" means nothing. | Seed (confirmed, Mode B) | Phase 0; §2.4 (new) |  | Open
TST8 | Medium | No automation or CI. The test suite is run at Phase 0 and at release only. New and changed templates need tests; contract and guard tests should run on every change. | Seed (confirmed, Mode B) | §7.1 |  | Open
TST9 | Medium | edvidura_walkthrough.py is run with real credentials. Review the script before running it. State where the credentials come from (a secrets manager, never a document), and run it against a demo tenant, not real learners' data. | Seed (confirmed, Mode B) | Phase 0; §0 Files | DEC-34, VER-62 | Open
CON11 | Low | Phase 1 check "Does a quiz result show a standalone banner anywhere?" — "standalone banner" is undefined, and its tracker column says "Dossier claim" though the dossier is a never-use source. Say what is being checked and why. | New in this run | Phase 1 table |  | Open
CON12 | Low | Phase 5 names base_shell.html as the template to extend. Not named in any earlier document; VERIFY the real base template name. | New in this run | §6.1 Jinja branch |  | Open
CON7 | Low | "The most important step for 'no errors'" over-claims. Integration defects also come from authentication, cookies inside an iframe, CSRF, tenancy and timing. Reframe the heading as the main defence against data-shape defects. | Seed (confirmed, Mode B) | Phase 3 heading |  | Open
CON9 | Low | Phase 1 owner and access. The designer joins "the visual checks" on the live deployment. State which environment and which accounts, under least privilege. | Seed (confirmed, Mode B) | Phase 1 | DEC-34 | Open
INT8 | Low | "Mock file — chosen by the team". Fix the naming convention now (one module per entity, as in the Lovable document's mock-data contract), or files multiply. | Seed (confirmed, Mode B) | §4.5 |  | Open
INT9 | Low | The list headed "JSON endpoints already in the code" includes /teacher/analytics.csv and /teacher/attempts.csv, which are CSV exports. Split into JSON endpoints and file exports. | New in this run | §4.3 |  | Open
LOV8 | Low | Visual edits and drafts. Edits made in Lovable's visual editor, or through drafts, bypass the prompt record. Ban them, or log them as prompt changes. | Seed (confirmed, Mode B) | §5.2 |  | Open
LOV9 | Low | Screenshot workload. Three widths for every screen and state, across 21+ batches, is hundreds of manual screenshots. Automate with a short Playwright script against the synced repository's local build. | Seed (confirmed, Mode B) | §5.3 |  | Open
LRN8 | Low | G4: omitting stickers is right. Record the reason (no gamification; the standard's principle 12), so it isn't reopened. | Seed (confirmed, Mode B) | Phase 2 G4 | DEC-38, VER-60 | Open
OPS5 | Low | Maintenance has no cadence or owner. "After each phase: update the tracker" — who, and when (for example, a weekly tracker review chaired by the senior developer)? | Seed (confirmed, Mode B) | Phase 8 | DEC-39 | Open
OPS6 | Low | Document control. Version 2 has a version and date but no owner, approver, audience, purpose statement or summary of changes from Version 1. | Seed (confirmed, Mode B) | Front matter |  | Open
OPS7 | Low | Readability for new graduates. No glossary pointer for AGS, RLS, LTI, JWKS, CSRF or Addendum V; some steps combine several actions. | Seed (confirmed, Mode B) | Appendix B (new); Front matter |  | Open
REF5 | Low | Unexplained references. "Authority section", "Addendum V", "Citrus Mint", "teleport link", "time capsule", "Feedback Assist", "stickers". A new graduate needs a one-line gloss or a pointer for each. | Seed (confirmed, Mode B) | Appendix B (new) |  | Open
REF6 | Low | File names carry no versions or dates. "FINAL" and "_reviewed" are not versions. Record version, date and owner per file in §0. | Seed (confirmed, Mode B) | §0 Files |  | Open

## Strengths
ID | Strength | Why it must survive
STR1 | §0 file-authority table with a status per file, plus an explicit "Never use" list (dossier, /static/..., internal pages, the demo password) | Stops the team building from stale or untrusted sources
STR2 | Phase 0 baseline before anything is built; historical test counts (265/295) must not be quoted until re-run | Evidence before claims
STR3 | Phase 1 runs live checks *before* design decisions, and passes results that change a screen to Phase 2 | Design follows reality, not documents
STR4 | Phase 3 builds the contract from the code — "field names are copied from the code, not from the documents" — and shapes mocks from the contract | The single best defence against integration defects
STR5 | Lovable discipline: no backend, database or auth in Lovable; one batch at a time; one problem per correction; reject renamed routes and invented copy | Saves credits and keeps the prototype faithful
STR6 | Acceptance includes screenshots at three widths, a keyboard pass, a screen-reader spot check, and a network-panel check | Accessibility and "no hidden backend" are tested, not assumed
STR7 | Phase 5 tests every screen with an account that should be refused, and treats a label or data difference from the accepted prototype as a defect | Guards are proven, and drift is caught
STR8 | Phase 8: a status becomes "Verified" only with a recorded result; feature and prompt documents are updated in the same change | Keeps the documents honest over time
STR9 | A summary table of phases, outputs and gates | Gives the whole process at a glance

## Change Table
Section | Before | After | Reason | Finding
Front matter | Title, subtitle with version and date | Document-control table: version 3, owner, approver, audience, purpose, status of facts, summary of changes | Document control | OPS6
Front matter | (none) | 'How to read this': steps, gates, ID types, Stop-and-ask convention | Readability for new graduates | OPS7
§0 Files | Three columns: file, use, status | Version/date/owner column added ('to fill' where unknown) | Files carry no versions | REF6
§0 Files | Tracker: decisions, checks, findings, changes | Also holds the API Contract and Gate Matrix tabs; marked 'the live record' | One source for gates and contract | SEQ1, OPS2
§0 Files | Learning Design Standard and Field Guide not listed | Both listed with status VERIFY (VER-66) | Readers must know whether to use them | REF2, LRN1
§0 Files | walkthrough script: 'Run it yourself' | 'Run it yourself, after review (Phase 0 step 3)' | Script runs with real credentials | TST9
§0 Never use | 'any /static/... path' | 'any path under /static/uploads/...' (tenant uploads); build assets may stay; VER-55 | The broad ban could remove the app's own CSS/JS/fonts | INT6
§0 Never use | 'the demo password in any document' | 'any password, key or token, in any document' | Covers all credentials | SEC1
§0A (new) | (none) | Environments table (local, staging, production); role accounts; secrets manager; staging first; approved and logged production checks; least privilege | Environments undefined; production probing unauthorised | OPS4, SEC3, DEC-34, DEC-35
§0B (new) | Owners named by role in each phase only | RACI table per phase incl. instructional designer, QA, DPO, juniors; sign-off per gate | No accountability matrix; juniors invisible | OPS1, OPS8
Phase 0 | Demo password handled at release (Phase 7) | Step 1–3: rotate now, search for copies, separate credentials per environment (VER-59) | A disclosed password stays valid until rotated | SEC1
Phase 0 | 'Run edvidura_walkthrough.py yourself' | Step 4: review the script first (VER-62); step 8: run on staging, production only under DEC-34 | Script uses real accounts | TST9, SEC3
Phase 0 | Record test counts with the date | Also record the commit SHA and environment | Evidence format | TST7
Phase 0 | 'Fix or record the two files' | Commit, revert or record with the senior developer's review | Uncommitted changes need review | STR2 kept
Phase 0 | 'Keep the REPORT.md and screenshots' | Store them in an access-controlled folder; never in chat or the documents folder | May contain learner personal data | SEC8
Phase 0 | 'Confirm the production host (audit claim 23)' | Recorded as VER-65 | Audit claims need tracker IDs | REF1
Phase 0 gate | Baseline recorded | Baseline with environment and commit; password rotated; script reviewed; signed by senior developer | Gate names its evidence and signer | SEC1, OPS1
Phase 1 | Run on the live deployment; designer joins the visual checks | Staging first; production only under DEC-34; designer works on staging; can run in parallel with Phase 3 | Least privilege; shorter critical path | SEC3, SEQ1, CON9
Phase 1 table | Top Learners: 'If yes, the product owner must decide' | If it exists, it is removed unless the product owner records a reason (VER-64) | It would be a leaderboard | LRN10
Phase 1 table | Audit claims 6, 7, 8 | VER-63, VER-61, VER-64 | Audit claims need tracker IDs | REF1
Phase 1 table | Time capsule: 'Format of the export' | Format, tenant scope and personal data | A data export needs privacy review | SEC5, INT10
Phase 1 table | Exposure checks (VER-45, VER-46): record result | 'If yes, follow §2.3 now' | Confirmed exposure is an incident | SEC2
Phase 1 table | 'Does a quiz result show a standalone banner anywhere?' / Dossier claim | Name the banner text from the Audit Report Verification before checking; the dossier is still never a source | Undefined check | CON11
Phase 1 table | Account column | Account and environment column | Environments explicit | OPS4
§2.2 (new) | (none) | Carried-in VERIFY items VER-02, 03, 07–10, 13, 20, 36–38 with VER-53/54 status check | Earlier blocking checks had no phase | REF3
§2.3 (new) | (none) | Incident path (DEC-33): stop, contain same day, record, DPO assesses under DPDP, fix, re-test, close | Exposure would otherwise wait for release | SEC2
§2.4 (new) | (none) | Evidence format: environment, SHA, role, IST time, request, result, stored evidence | 'Verified' needs evidence | TST7
Phase 1 gate | Only 'Confirmed' results that change a screen go to Phase 2 | Any result that differs from the documents (Confirmed or Disproved) | Disproved results can change screens too | CON5
Phase 1 gate | VER-44 to 50 recorded | Plus VER-61, 63, 64 and VER-53/54 answers; signer named | Complete gate | REF1, REF3
Phase 2 | One table of eight decisions | Three tables grouped by what they block: before any batch, before specific batches, before release | Gate lists disagreed | CON2, REF4
Phase 2 DEC-01 | 'Confirm' + 'unless the team chooses React'; Phase 5 'recommended in the current decision' | One statement: Open until VER-52 confirms; default = design reference, Jinja stays | DEC-01 was both open and decided | CON1
Phase 2 DEC-16 | 'Display vocabulary (School admin, Teacher, Student or the senior's Institute, Training Officer, Learner)' | Split: DEC-08 UI terminology (neutral options) and DEC-16 one learner vocabulary | Two decisions conflated; personalised option | CON10
Phase 2 DEC-16 | 'Use code values for everything the backend sends' | Display-mapping rule 3.2.1: code values in data, words from the strings file | Backend values were reaching learners | LRN3
Phase 2 DEC-27 | Adopt | Adopt after the contrast check (VER-57) | Light hues may fail contrast | LRN6
Phase 2 DEC-31 | Clamp accent lightness; white text 4.5:1; test six hues | Also accent text 4.5:1 on page/surfaces and focus/control edges 3:1; VER-57 | Incomplete contrast criteria | LRN6
Phase 2 G4 | 'G4 Stickers, teleport link, report-a-problem' | DEC-38: omit stickers; teleport and report-a-problem only after VER-60 and a privacy note | G4 not a tracker ID; features need security and privacy review | REF1, SEC5, LRN8
Phase 2 DEC-30 | Keep the constant | Keep it, say where 60% comes from on screen; per-course threshold to the Pedagogy Roadmap; instructional designer countersigns | Valid assessment | LRN2
Phase 2 DEC-28 | Remove the mount; serve files through authenticated routes | Move tenant uploads only; keep build assets; VER-55 first | Could break styling | INT6
Phase 2 DEC-29 | Decide per table | Criteria in 3.2.3: readers before/after tenant resolution, cross-tenant visibility, DB role, proving test | No criteria | SEC4
Phase 2 (new rows) | (not listed) | DEC-02, 03, 04, 05, 09, 10, 18, 19, 21, 22, 24, 26, 32–39 placed by what they block | Blocking decisions were missing | REF4
§3.3 (new) | 'Paste the batch as written; do not edit label text' with no update route | Apply signed decisions to the prompt document as a new version before pasting; record version per batch | Decisions could not reach the batches | CON4
Phase 2 gate | DEC-27 and DEC-16 before Part 0 | 'Before any batch' set before Batch 0; batch decisions before each batch; release decisions before R-gates; countersigners named | Gate lists disagreed | CON2
Phase 3 heading | 'the most important step for no errors' | 'the main defence against data-shape defects' | Over-claim | CON7
Phase 3 | Owner: senior developer | Juniors write rows, paired; senior reviews | Juniors' role explicit | OPS1
Phase 3 | 'all 188 routes' | Route count to be verified against Appendix A | Mode B — FINAL not opened | REF3
Phase 3 contract | Seven fields | Fifteen columns incl. kind, guard and scope, session, CSRF, enumerations, IDs shown, time, limits, errors, empty states | Missing the fields that break integrations | INT2
Phase 3 contract | Errors: status codes and messages | Real status code and template for denied/missing/other-institute records (VER-56) | App returns access.html | CON8
§4.2 (new) | (none) | Three worked examples: JSON /learn/coach/ask, page LR-06, form POST /quiz/submit (field names illustrative) | Juniors need a model row; pages have context, not JSON | INT3
§4.3 | 'JSON endpoints already in the code' (13, incl. two CSV) | Split into JSON endpoints and CSV file exports | Two items were not JSON | INT9
§4.4 (new) | Gate covered Appendix C screens only | Routes without a screen: LTI login/launch/JWKS/deep-link return/AGS/NRPS/return, onboarding, ops retry, data exports | Integration blind spot | INT4
§4.4 | receipt.json and time-capsule.json listed only as JSON endpoints | Personal-data notes; learner button 'Download receipt file'; VER-40, VER-61 | Exports need privacy rules | INT10
§4.5 (new) | (none) | Align Batch 0 mock modules with the contract before Batch 0; new prompt-document version; generate or check types | Mocks would diverge from the contract | SEQ2, INT7
§4.5 | 'Mock file: chosen by the team' | One module per entity in src/data/, same names in the contract | Files multiply | INT8
§4.6 (new) | (none) | Contract tests in CI | Manual comparison doesn't survive change | INT7
Phase 3 gate | Every Appendix C screen has a row | Per batch: batch screens complete and mocks aligned; whole phase: all screens + §4.4 routes before R1 | Per-batch gating | SEQ1, INT4
§5.1 Lovable setup | 'Create one Lovable project. Connect it to a GitHub repository so every accepted batch is saved as a commit.' | Dedicated workspace; access level recorded; public remixing off; new repo; two-way sync explained; lovable-sync branch on divergence | Matches Lovable docs (23 Oct 2026) | LOV2, LOV3, DEC-32
§5.1 | (none) | Protect the synced branch: only the Lovable app and senior developer push; no force-push | Accepted batches could change silently | LOV2
§5.1 | Paste Part 0 once | Also store hard rules in project Knowledge | Reduces drift | LOV4
§5.1 | (none) | Credit budget per batch; credits recorded | No stop rule for credits | LOV7
§5.1 step 3 | 'Do not paste anything else until Part 0 has produced a working shell' | Part 0 then Batch 0; VERIFY which builds the shell (VER-51); S1 only after the shell passes Batch 0's checklist | §5.1 and §5.2 disagreed | CON3
§5.2 | Confirm the batch's gate is closed (Phase 2) | Check the batch's row in Appendix A (decisions, VERIFY, contract, prompt-document version) | Per-batch gate | CON2, SEQ1
§5.2 | (none) | Tag the last accepted state before pasting | Revert point | LOV1, LOV7
§5.2 | (none) | Dependency and environment-file check against the previous tag | Lovable adds packages unasked | LOV6
§5.2 | Send one correction message | Plus: after two failed corrections, revert to the tag and re-prompt a smaller part | Credit stop rule | LOV7
§5.2 | (none) | No visual editor or drafts on accepted screens; log if unavoidable | Bypasses the prompt record | LOV8
§5.2 | 'commit it to GitHub with the batch ID in the message' | Tag the accepted state (e.g. accepted-S3); record tag and SHA in the tracker | Lovable commits through its own app; no per-change message | LOV1
§5.3 | Screenshots at three widths | Taken by a script (e.g. Playwright) and stored with the tag | Manual workload | LOV9
§5.3 | 'The network panel shows no requests during mock flows' | No request to any API, auth, database or third-party data host; own assets and preview connections allowed | False failures | LOV5
§5.3 | 'No route in the prototype is a /static/... path' | No route or link to /static/uploads/..., /requirements-board, /session-today | Aligns with corrected ban | INT6
§5.3 (new items) | (none) | Learning check: intent, vocabulary, no system terms, practice vs graded, no gamification, no roadmap features | Learning design absent | LRN1
§5.3 (new items) | (none) | India check: IST, Indic rendering, throttled run shows loading states | India context absent | LRN7
§5.4 | Four pitfalls | Plus: silent changes via pushes to the synced branch | Two-way sync | LOV2
§5.5 (new) | (none) | Usability round: five ITI trainees, two instructors, on their phones | No user validation | LRN4
§5.5 (new) | (none) | Trade-content review by a qualified trade instructor (DEC-26, VER-35) | Unsafe electrical content | LRN5
Phase 4 gate | All batches accepted, committed, recorded | Accepted, tagged, recorded; usability round and content review recorded; signers named | Complete gate | LOV1, LRN4
§6.1 Jinja branch | 'rebuild each accepted batch as a Jinja template extending base_shell.html' | Change each existing template; do not rebuild routes/guards/handlers; context changes only via a logged contract defect; keep tests passing; VERIFY base template name | Greenfield wording invited rewriting working code | INT1, CON12
§6.1 React branch | 'Build the API layer first' | Lists the blockers: JSON for HTML pages, CSRF, iframe cookies (DEC-22), LTI bootstrap, CSP; follow DEC-01 record | Understated work | INT5
§6.2 step 1 | 'Implement the route or the template with the guard' | 'Change the template (or build the component), keeping the route and guard' | Routes already exist | INT1
§6.2 step 3 | 'a difference in label or data is a defect' | Label, structure or state differences are defects; data values are not | Mock data never equals real data | CON6
§6.2 step 4 | 'Any unexpected field is a defect' | Missing, renamed or re-typed fields are defects; extra fields recorded; forbidden fields on screen are defects | Too strict and too loose | CON6
§6.3 (new) | (none) | Ten-point Definition of Done per screen (DEC-36) | Done was scattered across four phases | OPS2
Phase 5 gate | Every screen connected, tested, recorded | Every screen meets the Definition of Done; signed by senior developer and QA (R1) | Gate names evidence | OPS2
§7.1 (new) | Five verification steps | Test plan: unit/contract, guards, cross-tenant/IDOR, course scope, LTI, AGS, onboarding, security, exposure re-check, accessibility, performance, learner loop, regression, walkthrough | Missing the biggest risks | TST1, TST2, TST4, TST5, TST6, TST10
§7.1 | 'no account reaches /ops/* without the key' | '/ops/* refuses without operator sign-in' (DEC-21 may replace the shared key) | Avoid entrenching the shared key | SEC6
§7.1 | (none) | CI runs unit, contract, guard and cross-tenant tests on every change; dependency and secret scanning | No automation | TST8, SEC6
§7.2 (new) | (none) | LTI environment matrix: Chrome, Edge, Firefox, Safari macOS/iOS, Moodle app Android × iframe/new window × three roles; session expiry mid-quiz | No LTI matrix | TST3
Phase 6 gate | All tests pass or failures recorded with an owner | Same, plus a date; signed by senior developer and QA | Signer named | OPS1
§8.1 Release | Five confirmations | Release gates R1–R5 with decisions, VERIFY items and signers; privacy notice and DPDP items | Release gate incomplete | SEC7, OPS3, OPS8
§8.1 | 'The demo password is removed from the audit report' | No document contains any credential and the old password no longer works (VER-59) | Removal is not revocation | SEC1
§8.1 R3 | (none) | Grade passback proven, or honest messages everywhere | AGS never verified | TST2
§8.2 (new) | (none) | Rollout plan: backup and restore test, migration order with rollback, pilot (one institute/trade/cohort), learning-gain baseline, monitoring and alerts, rollback trigger and owner, support route, training, communication | No operations plan | OPS3, LRN9, DEC-37
§8.3 (new) | Owner: product owner and senior developer | Release signed after QA, DPO and instructional designer sign R1–R5 | Release sign-off too narrow | OPS8
Phase 8 | One paragraph | Numbered steps; weekly tracker review; document owners table; change control (DEC-39) | No cadence, owners or freeze rule | OPS5, SEQ5
§10 Summary | Gate for Phase 2: 'DEC-27 and DEC-16 before Part 0' | Matches every phase gate; signer column added | Summary disagreed with the phases | CON2
§11 (new) | (none) | Re-entry rules table | No way back when a later phase finds an earlier error | SEQ3
§12 (new) | (none) | Critical path with parallel lanes; effort ranges as assumptions | No critical path or estimates | SEQ1, SEQ4
Appendix A (new) | (none) | Gate and Dependency Matrix summary; full matrix in tracker tab 'Gate Matrix' | Per-batch gating | CON2, SEQ1
Appendix B (new) | (none) | Glossary incl. authority section, Addendum V, Citrus Mint, teleport link, time capsule, Feedback Assist, stickers, Training Officer | Unexplained references | REF5, OPS7