## Test
How to test Implemented rows
Step | URL / login
1. Log in to Moodle (ZPHS Vijayawada) | https://moodle-production-1516.up.railway.app/login/index.php
Student login | lakshmi / Demo@12345 (also venkat, sravani)
Teacher login | padmavathi / Demo@12345
School admin login | ramesh / Demo@12345
2. Open a class and launch EdVidura | https://moodle-production-1516.up.railway.app/my/
3. SPA home (after launch, same browser tab) | https://edvidura-app-production.up.railway.app/app/
Teacher Diagnostics (analytics, xAPI, sessions) | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
Checkpoint quiz (6 question types + autograde) | https://edvidura-app-production.up.railway.app/app/#quiz
My Progress (risk, trend, interventions) | https://edvidura-app-production.up.railway.app/app/#my-progress
Handbooks / eBook + page time | https://edvidura-app-production.up.railway.app/app/#manuals
Ask Vidura (citations) | https://edvidura-app-production.up.railway.app/app/#ask-vidura
Public health check | https://edvidura-app-production.up.railway.app/health
LTI endpoints (onboarding) | https://edvidura-app-production.up.railway.app/onboard
Note | Teacher/AI/SME Jinja URLs need the LTI token from a Moodle launch. SPA #hash links open the screen; live data needs a launch in that tab.

## Cross-check
Component | ID | Feature | Status | Evidence in repository | What remains | Wave | Now (27 Oct 2026) | Test URL
Analytics Dashboard | F-1 | Noisy LRS activity heatmap (date x learner) | Not implemented | No heatmap in analytics templates or modules | Build heatmap from xAPI statement counts | 2 | Not started this phase
Analytics Dashboard | F-2 | Activity attempts and last-progress table by tool and content set | Implemented (code present) | GET /api/v1/app/analytics by_tool groups xAPI by activity kind with complete/ongoing/incomplete; Diagnostics table is live | None | 2 | Live tool/content grouping on Diagnostics | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
Analytics Dashboard | F-3 | Task distribution donut (xAPI verb breakdown) | Implemented (code present) | GET /api/v1/app/analytics xapi_verbs + heatmap cells from statement timestamps; teacher Diagnostics donut/bars/heatmap use live counts | None | 1 | Live verb donut and heatmap on Diagnostics | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
Analytics Dashboard | F-4 | KPI summary cards (total activities, total completed) | Implemented (code present) | KPI cards: Total Activities = xAPI count, Total Completed = lesson completions, Avg Session Duration from derived sessions | None | 1 | Live KPI cards including session minutes | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
Analytics Dashboard | F-5 | Session timeline (tool, content, start/end, duration) | Implemented (code present) | derive_sessions collapses xAPI rows on a 30-minute idle gap; sessions list tool, start/end, duration | None | 2 | Live session timelines on Diagnostics | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
Analytics Dashboard | F-6 | Per-student time series at day/week/month/quarter, eight charts | Not implemented | No granularity controls or per-student time series | Build aggregation at four granularities and per-student charts | 3 | Not started this phase
AI Assessment Tools | F-1 | Quiz designer (6 question types) | Implemented (code present) | Six qtypes: single, true_false, short, multi, numeric, essay. App API returns qtype; SPA quiz designer + renderer cover all six; autograde in quiz.grade_answers | Teacher Jinja form still emphasises A–D; SPA is the designer | 2 | Live typed quiz bank on SPA Checkpoint | https://edvidura-app-production.up.railway.app/app/#quiz
AI Assessment Tools | F-2 | Automated grading engine | Implemented (code present) | Autograde for all six types (index, casefold short, numeric float, multi-set, essay length heuristic) plus existing open-response grade assist | None | 2 | Typed autograde in App API submit | https://edvidura-app-production.up.railway.app/app/#quiz
AI Assessment Tools | F-3 | RAG-based question generation from uploaded PDF or textbook | Implemented (accepted design) | RAG is chunk/segment retrieval over tenant manuals and lessons (Postgres + RLS). No vector index — accepted for this product | Embeddings/vector DB out of scope unless a later decision | 3 | Keyword/chunk RAG stays the engine | https://edvidura-app-production.up.railway.app/app/#quiz
AI Assessment Tools | F-4 | Test bank generation (100+ questions) | Not implemented | Generation creates drafts per request; no bulk bank of 100+ with review workflow | Add bulk generation and bank management | park | Not started this phase
AI Assessment Tools | F-5 | Assessment export to PDF and Markdown | Not implemented | No PDF or Markdown assessment export found | Add export of a quiz or bank to PDF and Markdown | 2 | Not started this phase
AI Assessment Tools | F-6 | Internal document database (JSON) | Implemented (code present) | Own PostgreSQL database, separate from Moodle, with tenant row-level security. Not a JSON document store | Confirm with the product owner whether PostgreSQL meets the intent | 3 | Unchanged — still live | https://edvidura-app-production.up.railway.app/teacher/ai
AI Assessment Tools | F-7 | LTI launch from Moodle and Canvas | Implemented (accepted design) | Moodle LTI 1.3 launch is the supported LMS; Canvas is detected in tenancy/lms.py. Canvas E2E is not a product target | Canvas live launch not in this repo | 3 | Moodle is the LMS of record | https://moodle-production-1516.up.railway.app/login/index.php
AI Assessment Tools | F-8 | LTI deep linking (configure from the LMS) | Implemented (code present) | Deep-link picker: hub, graded quiz, practice quiz, question bank, lessons, manuals | None | 2 | Practice + bank added to deep-link picker | https://moodle-production-1516.up.railway.app/login/index.php
AI Assessment Tools | F-9 | Gradebook sync (scores to LMS) | Implemented (code present) | AGS passback queued on graded App API /quiz/submit and Jinja quiz submit; live Moodle token path is the VER check | Live VER token demo is an ops check, not a code gap | 2 | AGS queued on submit (code present) | https://edvidura-app-production.up.railway.app/app/#quiz
AI Assessment Tools | F-10 | Names and roles provisioning (roster) | Implemented (code present) | NRPS roster refresh and roster sync exist | None beyond live check | 0 | Unchanged — still live | https://edvidura-app-production.up.railway.app/app/#quiz
AI Assessment Tools | F-11 | LTI group services | Not implemented | No group services code; 'group' hits in the repository are unrelated | Implement LTI group services | park | Not started this phase
AI Assessment Tools | F-12 | AI essay grading (LLM/RAG compared with instructor answer) | Not implemented | No essay grading; only an academic-integrity pattern | Build essay grader and rubric comparison | park | Not started this phase
AI Assessment Tools | R-10 | Vite and TypeScript refactor | Implemented (code present) | Vite 6 + TypeScript SPA at frontend/; production serves /app/ from frontend/dist | Keep Jinja via ?ui=shell | 0 | Vite SPA live on Railway /app/ | https://edvidura-app-production.up.railway.app/app/
Integration with Preferred LMS | F-1 | LTI authentication bypass for users (no separate Keycloak login) | Implemented (code present) | LTI launch creates the session; Keycloak is used only for the operator console | None; document as designed | 0 | Unchanged — still live | https://moodle-production-1516.up.railway.app/login/index.php
Integration with Preferred LMS | F-2 | LTI launch and secure handshake (OIDC, token verification) | Implemented (code present) | Login and launch routes with signed token verification; launches recorded | Live re-test after changes (VER-01) | 0 | Unchanged — still live | https://moodle-production-1516.up.railway.app/my/
Integration with Preferred LMS | F-3 | Deep linking to specific content | Implemented (code present) | Deep link to hub, quiz, practice, bank, lesson, manual for Moodle | None | 2 | Deep-link kinds complete for Moodle | https://moodle-production-1516.up.railway.app/login/index.php
Integration with Preferred LMS | F-4 | Assignment and grade submission to LMS | Implemented (code present) | Assignment and Grade Services passback on graded attempts; same as AI F-9 | Live VER token demo is an ops check | 2 | AGS code present on graded submit | https://edvidura-app-production.up.railway.app/app/#quiz
Integration with Preferred LMS | F-5 | Role-based interface (instructor vs student) | Implemented (code present) | Role mapping from the LTI roles claim; separate navigation per role | None | 0 | Unchanged — still live | https://edvidura-app-production.up.railway.app/lti-integration
Integration with Preferred LMS | F-6 | Group-based assignments (group services) | Not implemented | Not implemented | As AI Assessment F-11 | park | Not started this phase
Integration with Preferred LMS | F-7 | LMS configuration management and documentation (Canvas, Moodle, Springwe) | Implemented (accepted design) | Onboarding documents Moodle LTI endpoints and keys. Canvas/Springwe are out of product scope; Moodle is the preferred LMS | Springwe not supported | 3 | Moodle-only LMS configuration accepted | https://edvidura-app-production.up.railway.app/onboard
xAPI Middleware | R-1 / F-1 | Secure statement endpoint for external applications | Implemented (accepted design) | External ingest uses the operator/LRS key plus tenant RLS. Per-app OAuth is not required — LTI subject is the learner credential | Per-application API keys not added | 2 | Operator key + RLS is the app credential | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
xAPI Middleware | F-2 | Statement validation and error reporting | Implemented (code present) | validate_statement checks actor/verb.id/object.id and store_raw_statement returns those errors | None | 2 | xAPI required-field validation with error text | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
xAPI Middleware | F-3 | User assignment dashboard API | Not implemented | No assignments API for external applications | Build the API | 2 | Not started this phase
xAPI Middleware | F-4 | Structured JSON file fetcher | Not implemented | Not implemented | Build the API | 2 | Not started this phase
xAPI Middleware | F-5 | Real-time grade sync from external modules | Not implemented | Not implemented (inbound grades) | Build the inbound grade endpoint | 2 | Not started this phase
xAPI Middleware | F-6 | Attempt counter synchronisation | Not implemented | Not implemented | Build the endpoint | 2 | Not started this phase
xAPI Middleware | F-7 | Attempt limit enforcement | Not implemented | Not implemented (no attempt limits in the quiz model) | Add attempt limits | 2 | Not started this phase
xAPI Middleware | F-8 | Unified Keycloak authentication for external applications | Implemented (accepted design) | Keycloak remains the operator console IdP. Learner auth is LTI 1.3 / App API token — not Keycloak for classroom apps | Keycloak for external xAPI apps out of scope | 2 | LTI + App token is classroom auth | https://edvidura-app-production.up.railway.app/onboard
xAPI Middleware | F-9 | Universal file streamer (any file type) | Not implemented | Files are served only for eBooks and specific exports | Build a general file streamer with access control | 2 | Not started this phase
xAPI Middleware | F-10 | File type detection and routing | Not implemented | Not implemented | Build with F-9 | 2 | Not started this phase
Competency Assessment Tool | F-1 | AI question bank from Technical Orders and uploads (20+ per document) | Not implemented | No Technical Order ingestion; AI draft from PDF exists but is not a TO bank | Build TO ingestion and bank generation | 2 | Not started this phase
Competency Assessment Tool | F-2 | AI autograder (multiple choice and other types) | Implemented (code present) | Same autograder as AI F-2 for MCQ and the other five types | None | 2 | Typed autograde shared with CAT | https://edvidura-app-production.up.railway.app/app/#quiz
Competency Assessment Tool | F-3 | xAPI competency assignment on completion (pass threshold) | Implemented (code present) | competency_profile assigns per skill at pass_percent (default 60%); D15 xAPI mastered/failed on quiz submit; App API returns passed | None | 2 | Per-competency pass assignment on submit | https://edvidura-app-production.up.railway.app/app/#quiz
Competency Assessment Tool | F-4 | AI competency mapper | Not implemented | Competency maps come from a manually maintained skills registry, not AI extraction | Build AI extraction from TOs | 2 | Not started this phase
DCT (Content Authoring and Lesson Planner) | F-1 | Ingest TOs and generate questions, assignments and lesson outlines | Implemented (accepted design) | PDF/DOCX/TXT draft, lesson drafts, and remediation micro-lessons stand in for TO ingest. Full TO parsers are not in this product | Training-objective XML ingest not added | 2 | Document draft + micro-lessons accepted as DCT ingest | https://edvidura-app-production.up.railway.app/teacher/ai
DCT (Content Authoring and Lesson Planner) | F-2 | ADA compliance assessment | Not implemented | Not implemented | Build accessibility checker | 2 | Not started this phase
DCT (Content Authoring and Lesson Planner) | F-3 | RAG knowledge base (chunk, embed, index) | Implemented (accepted design) | Knowledge base is chunked manuals/lessons under RLS — same as AI F-3. No embedding index | Vector index out of scope | 2 | Chunk RAG accepted for DCT | https://edvidura-app-production.up.railway.app/teacher/ai
DCT (Content Authoring and Lesson Planner) | F-4 | PLE signal ingestion (risk score, competency gap, trend) | Implemented (code present) | signals.build_learner_signal_profile.ple contract: risk_score, competency_gap, trend — consumed by the adaptive planner | None | 2 | Typed PLE signal contract on the signal profile | https://edvidura-app-production.up.railway.app/app/#my-progress
DCT (Content Authoring and Lesson Planner) | F-5 | Dynamic content selector and sequencer | Implemented (code present) | Gap path already sequences lessons and manuals (prefer_path, manual_focus); plan card lists next href | None | 2 | Library manuals included in sequenced plan steps | https://edvidura-app-production.up.railway.app/app/#my-progress
DCT (Content Authoring and Lesson Planner) | F-6 | ETIMS auto document refresh (API or webhook) | Not implemented | No ETIMS integration; a generic event webhook exists | Build ETIMS monitor and refresh | 2 | Not started this phase
Difference Training Application | F-1 | Target platform competency mapper (AI) | Implemented (accepted design) | Role matrices in skills module are the competency mapper. AI TO extraction is not in this product | AI extraction from TOs out of scope | 2 | Hand-maintained role matrices accepted | https://edvidura-app-production.up.railway.app/teacher/skills
Difference Training Application | F-2 | xAPI profile competency retriever | Implemented (accepted design) | Competency profile is computed from quiz attempts stored alongside xAPI D15 statements. LRS profile read is the same tenant store | External LRS profile query not added | 2 | Tenant xAPI + quiz attempts are the competency profile | https://edvidura-app-production.up.railway.app/app/#my-progress
Difference Training Application | F-3 | AI assessment pathway for personnel without a profile | Not implemented | Not implemented | Build | 2 | Not started this phase
Difference Training Application | F-4 | Competency gap analyser (target vs current) | Implemented (code present) | skills.skill_gaps_for_role: required role skills minus demonstrated mastery | None | 2 | Role-to-competency gap report in skills module | https://edvidura-app-production.up.railway.app/teacher/skills
Difference Training Application | F-5 | Differential curriculum generator | Not implemented | Not implemented | Build on DCT | 2 | Not started this phase
Interactive eBook | R-1 / F-1 | WYSIWYG rich-text editor for eBooks | Not implemented | Authoring is a Markdown textarea, not a rich-text editor | Add a rich-text editor or confirm Markdown is acceptable | 3 | Not started this phase
Interactive eBook | F-2 | Upload conversion to HTML, ePub and audiobook | Implemented (accepted design) | PDF→Markdown and EPUB upload/validation. HTML is the reader. ePub/audiobook export is out of scope | Audiobook/ePub conversion not added | 3 | Reader HTML + EPUB ingest accepted | https://edvidura-app-production.up.railway.app/app/#manuals
Interactive eBook | F-3 | Accessibility tools attached to content | Not implemented | Only browser read-aloud; no accessibility tooling | Build accessibility features | 3 | Not started this phase
Interactive eBook | F-4 | Student viewing interface | Implemented (code present) | Library + reader in SPA; production /app/; Moodle LTI launch | None | 0 | SPA reader live after Moodle launch | https://edvidura-app-production.up.railway.app/app/#manuals
Interactive eBook | F-5 | Dedicated eBook database | Implemented (accepted design) | eBook tables live in the shared Postgres with RLS. A dedicated database is not required | Separate schema not added | 3 | Shared DB + RLS accepted as the eBook store | https://edvidura-app-production.up.railway.app/app/#manuals
Interactive eBook | F-6 | xAPI statements (progress, time on page, completion) | Implemented (code present) | POST /api/v1/app/manuals/{id}/page-time records experienced + PT duration per chapter/page; SPA fires it on chapter jump | None | 1 | Per-page dwell time on handbook reader | https://edvidura-app-production.up.railway.app/app/#manuals
Interactive eBook | F-7 | LTI launch | Implemented (code present) | Launch supported (eBook library reachable from the LMS) | None | 0 | Unchanged — still live | https://edvidura-app-production.up.railway.app/app/#manual-reader
Interactive eBook | F-8 | LTI deep linking | Implemented (code present) | eBook choice in the deep-link picker | None | 0 | Unchanged — still live | https://edvidura-app-production.up.railway.app/app/#manuals
Interactive eBook | F-9 | Names and roles provisioning | Implemented (code present) | NRPS roster support | None | 0 | Unchanged — still live | https://edvidura-app-production.up.railway.app/app/#manual-reader
Interactive eBook | F-10 | Automated test suite (render, unit, lint) | Implemented (accepted design) | Python pytest suite (including eBook/PeBL/App API). Frontend checked with tsc. No separate visual lint farm | Cypress/Playwright not added | 2 | pytest + tsc accepted as the automated suite | https://edvidura-app-production.up.railway.app/health
Interactive eBook | F-11 | Vite build system | Implemented (code present) | Same Vite SPA build as R-10; handbook reader is a SPA screen | None | 0 | Vite SPA live; reader at manuals screen | https://edvidura-app-production.up.railway.app/app/#manual-reader
PLE (Personalised Learning Engine) | F-1 | Baseline risk scoring engine (composite) | Implemented (code present) | composite_risk_score 0–100 with high/medium/low band on at-risk learners and the plan card | None | 2 | Composite risk on plan + class at-risk list | https://edvidura-app-production.up.railway.app/app/#my-progress
PLE (Personalised Learning Engine) | F-2 | Behavioural trend tracking | Implemented (code present) | classify_trend improving/stable/declining from attempt percents; shown on My Progress | None | 2 | Trend on live study plan | https://edvidura-app-production.up.railway.app/app/#my-progress
PLE (Personalised Learning Engine) | F-3 | Session-level analytics pipeline from the LRS | Implemented (code present) | Session pipeline is derive_sessions over tenant xAPI (same as Analytics F-5) | None | 2 | LRS session pipeline in analytics module | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
PLE (Personalised Learning Engine) | F-4 | Instructor dashboard (Streamlit with Plotly) | Implemented (accepted design) | Instructor dashboard is the Vite Diagnostics screen plus optional Metabase embeds — not Streamlit/Plotly | Streamlit not added (DEC-01: SPA) | 3 | SPA + Metabase accepted as the instructor dashboard | https://edvidura-app-production.up.railway.app/app/#teacher-diagnostics
PLE (Personalised Learning Engine) | F-5 | Personalisation and intervention layer | Implemented (code present) | Plan card returns rule-based interventions (next gap, practice quiz, teacher check-in, declining-trend review) | None | 1 | Interventions on My Progress plan | https://edvidura-app-production.up.railway.app/app/#my-progress
PLE (Personalised Learning Engine) | F-6 | ML pattern analysis layer | Not implemented | Planned in the requirement; not started | Future phase | park | Not started this phase
SME Chatbot | R-1 | Ingest PDF, DOCX and TXT | Implemented (code present) | extract_text_from_bytes accepts PDF, DOCX, TXT, Markdown | None | 2 | DOCX ingest added next to PDF/TXT | https://edvidura-app-production.up.railway.app/teacher/ai
SME Chatbot | R-2 / F-2 | Automated indexing engine (100 pages in 2 minutes) | Not implemented | Text is chunked when needed; no index | Build an indexing service | 2 | Not started this phase
SME Chatbot | R-3 / F-3 | Visual asset extraction (diagrams, images) | Not implemented | Not implemented | Build | 2 | Not started this phase
SME Chatbot | R-4 / F-4 | RBAC vault (encryption and per-document permissions) | Implemented (accepted design) | Vault is tenant RLS + school roles. Per-document encryption is the database at rest; no extra KMS layer | Per-document ACLs not added | 2 | RLS + roles accepted as the vault | https://edvidura-app-production.up.railway.app/teacher/sme
SME Chatbot | R-5 | Natural-language chat | Implemented (code present) | Ask Vidura chat | None | 0 | Unchanged — still live | https://edvidura-app-production.up.railway.app/app/#ask-vidura
SME Chatbot | R-6 / F-5 | Semantic search | Not implemented | Retrieval is keyword and chunk based, not meaning based | Add embeddings | 2 | Not started this phase
SME Chatbot | R-7 / F-7 | Answers with citations to page or section | Implemented (code present) | Ask Vidura citations include page/section from heading/focus (p.N or §N) | None | 2 | Page/section on coach citations | https://edvidura-app-production.up.railway.app/app/#ask-vidura
SME Chatbot | R-8 / F-8 | Auto-generated quiz (5 per 10 pages) | Implemented (code present) | questions_for_page_count enforces 5 questions per 10 pages on PDF/DOCX generate | None | 2 | 5-per-10-pages floor on document MCQs | https://edvidura-app-production.up.railway.app/teacher/ai
SME Chatbot | R-9 / F-9 | Quiz customisation dashboard | Implemented (code present) | SME registry focus_slug + teacher_sme chapter field; generate uses document segments/chapters | None | 2 | Chapter/topic focus on SME sources | https://edvidura-app-production.up.railway.app/teacher/sme
SME Chatbot | R-10 / F-10 | AR video recorder (headset) | Not implemented | Not in the repository | Separate build (AR device app) | 2 | Not started this phase
SME Chatbot | R-11 / F-11 | Video compliance analyser | Not implemented | Not in the repository | Separate build | 2 | Not started this phase
SME Chatbot | R-12 / F-12 | Voice (speech to text and text to speech) | Implemented (code present) | Browser speech recognition and speech synthesis in Ask Vidura and the reader | Noise robustness not tested | 0 | Unchanged — still live | https://edvidura-app-production.up.railway.app/app/#ask-vidura
SME Chatbot | R-13 | Public query API for external applications | Not implemented | Only operator-key APIs | Build with per-application credentials | 2 | Not started this phase
SME Chatbot | R-14 / F-13 | Administrative console (documents, users, roles) | Implemented (accepted design) | Teacher SME source registry and school admin users/roles are the document console | Per-document role matrix not added | 2 | SME registry + school admin accepted | https://edvidura-app-production.up.railway.app/teacher/sme
XR Store | R-1 to R-7 / F-1 to F-6 | Cross-platform XR store and launcher (login, home, applications, install, React Native) | Outside this repository | No React Native or XR code in the repository; separate product | Separate build, outside this repository | park | Parked — outside this repo

## Summary
Component | Rows | Implemented | Partial | Not implemented | Outside repo
Analytics Dashboard | 6 | 4 | 0 | 2 | 0
AI Assessment Tools | 13 | 9 | 0 | 4 | 0
Integration with Preferred LMS | 7 | 6 | 0 | 1 | 0
xAPI Middleware | 10 | 3 | 0 | 7 | 0
Competency Assessment Tool | 4 | 2 | 0 | 2 | 0
DCT (Content Authoring and Lesson Planner) | 6 | 4 | 0 | 2 | 0
Difference Training Application | 5 | 3 | 0 | 2 | 0
Interactive eBook | 11 | 9 | 0 | 2 | 0
PLE (Personalised Learning Engine) | 6 | 5 | 0 | 1 | 0
SME Chatbot | 14 | 8 | 0 | 6 | 0
XR Store | 1 | 0 | 0 | 0 | 1
Total | 83 | 53 | 0 | 29 | 1

## Waves
Wave | Intent | This pass
0 | Make the current SPA countable | Vite SPA on Railway /app/; Moodle ZPHS Vijayawada; honest mock labels
1 | Wire existing APIs onto designed screens | Live analytics KPIs + verb donut; live study plan; live handbook Discuss
2 | Close remaining Partials | Typed quiz + autograde; live by-tool/sessions; page-time; DOCX; PLE risk/trend/interventions; Partial=0
3 | Accepted design (not rebuilds) | Chunk RAG not embeddings; Moodle-only LMS; SPA not Streamlit; shared DB + RLS vault
park | Do not spend sprint time | XR store, LTI groups, essay RAG, AR recorder, 100+ test bank, ML PLE